## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1568/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 29.22 | 0 | 0 | 0
2 | JHARGRAM | Jamboni | Jhargram Mechanical Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | New Service connection |  |  | BILL/00412/2023-2024 | 7/JMD | 07/09/2023 | 07/09/2023 | WBSEDCL | 3.25 | 0 | 0 | 0
3 | JHARGRAM | Jamboni | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line,Installation of display Board, soil investigation ,including 02(Two) Years Operation & Maintenance & Accommodate FHTC (1440 nos) under JJM with allied work for Parihati PWSS in Jamboni Block including supply of all labour & materials within Jhargram Sub- Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000102/2023-2024 | 1202/JHD | 26/07/2023 | 22/01/2024 | SAIKAT DANDAPAT | 362.99 | 0 | 0 | 5
4 | JHARGRAM | Jamboni | Jhargram Division | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Parihati and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division,Junior Engineer-III | ORD/000578/2023-2024 | 514/JRWS | 15/03/2024 | 14/05/2024 | SANKAR KUMAR NAG | 4.82 | 0 | 0 | 0
5 | JHARGRAM | Jamboni | Central Drilling | PARIHATI AND ADJOINING MOUJAS PWSS | SM/12455 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 18.71 | 0.09 | 11
Total | [13 empty] | 21740.06 | 18.71 | 0.09