## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | SIJUA AND ADJOINING MOUJAS PWSS | SM/12519 | New | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 1534/JHD | 06/09/2023 | 06/09/2023 | Resource Division | 17.07 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I | Jhargram Division | SIJUA AND ADJOINING MOUJAS PWSS | SM/12519 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Sijua and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000058/2024-2025 | 771/JSD | 09/08/2024 | 08/09/2024 | M/S S.B. ENTRPRISE | 4.54 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | SIJUA AND ADJOINING MOUJAS PWSS | SM/12519 | New | NEW SERVICE CONNECTION CHARGES FOR SIJUA T/W - I PWSS |  |  | BILL/01386/2023-2024 | 50/JMD | 12/03/2024 | 12/03/2024 | WBSEDCL | 4.98 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | SIJUA AND ADJOINING MOUJAS PWSS | SM/12519 | New | NEW SERICE CONNECTION CHARGES FOR SIJUA T/W -II PWSS |  |  | BILL/01387/2023-2024 | 51/JMD | 12/03/2024 | 12/03/2024 | WBSEDCL | 5.28 | 0 | 0 | 0
Total | [13 empty] | 31.88 | 0 | 0