## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Mechanical Division | BAGMURI AND ADJOINING MOUJAS PWSS | SM/12523 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bagmuri & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000213/2023-2024 | 1228/JMD | 26/05/2023 | 22/11/2023 | ARATI ENGINEERING | 20.76 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Division | BAGMURI AND ADJOINING MOUJAS PWSS | SM/12523 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
3 | JHARGRAM | Jhargram | Jhargram Division | BAGMURI AND ADJOINING MOUJAS PWSS | SM/12523 | New | Construction of boundary wall and Allied works At Dahatmal,Bagmuri,Champasol 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000097/2024-2025 | 1280/JHD | 03/09/2024 | 03/10/2024 | PROVAT KUMAR DE | 37.25 | 1.34 | 3.61 | 30
4 | JHARGRAM | Jhargram | Central Drilling | BAGMURI AND ADJOINING MOUJAS PWSS | SM/12523 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Driller In Charge | Junior Engineer | ORD/000001/2024-2025 | 91/CDD | 25/04/2024 | 25/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 20.18 | 13.02 | 10
5 | JHARGRAM | Jhargram | Jhargram Mechanical Division | BAGMURI AND ADJOINING MOUJAS PWSS | SM/12523 | New | NEW SERVICE CONNECTION CHARGES AT BAGMURI-II WATER SUPPLY |  |  | BILL/01578/2024-2025 | 501/JMD | 10/02/2025 | 10/02/2025 | WBSEDCL | 2.97 | 0 | 0 | 0
6 | JHARGRAM | Jhargram | Jhargram Mechanical Division | BAGMURI AND ADJOINING MOUJAS PWSS | SM/12523 | New | NEW SERVICE CONNECTION CHARGES AT BAGMURI-I WATER SUPPLY |  |  | BILL/01577/2024-2025 | 500/JMD | 10/02/2025 | 10/02/2025 | WBSEDCL | 4.73 | 0 | 0 | 0
Total | [13 empty] | 12505.49 | 21.53 | 0.17