## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Mechanical Division | MANTIPA & IT'S ADJOINING MOJAS PWSS | SM/12525 | New | NEW SERVICE CONNECTION CHARGES AT MANTIPA-II WATER SUPPLY SCHEME |  |  | BILL/00352/2024-2025 | 155/JMD | 31/05/2024 | 31/05/2024 | WBSEDCL | 3.5 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Mechanical Division | MANTIPA & IT'S ADJOINING MOJAS PWSS | SM/12525 | New | NEW SERVICE CONNECTION CHARGES AT MANTIPA-1 WATER SUPPLY SCHEME |  |  | BILL/00351/2024-2025 | 154/JMD | 31/05/2024 | 31/05/2024 | WBSEDCL | 7.08 | 0 | 0 | 0
3 | JHARGRAM | Jhargram | Jhargram Division | MANTIPA & IT'S ADJOINING MOJAS PWSS | SM/12525 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 9.84 | 0.08 | 25
Total | [13 empty] | 12295.35 | 9.84 | 0.08