## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-I,Sankrail | Jhargram Division | NOAGOAN AND ADJOINING MOUJAS PWSS | SM/12526 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House , & Providing Functional Household Tap Connection (6745 Nos), etc. For RAGRA, SATKULI CHARAR, NOAGAON, RAMPURA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000008/2023-2024 | 607/JHD | 04/05/2023 | 09/05/2026 | GOBINDA MAITY | 1886.45 | 349.14 | 18.51 | 20
2 | JHARGRAM | Gopiballavpur-I,Sankrail | Central Drilling | NOAGOAN AND ADJOINING MOUJAS PWSS | SM/12526 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | JHARGRAM | Gopiballavpur-I,Sankrail | Jhargram Mechanical Division | NOAGOAN AND ADJOINING MOUJAS PWSS | SM/12526 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Noagaon & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte in the dist. of Jhargram. | Driller-In-Charge | Junior Engineer | ORD/000204/2023-2024 | 2265/JMD | 09/08/2023 | 05/02/2024 | ORIENTAL ENGINEERING CO. | 22.08 | 18.75 | 84.93 | 94
4 | JHARGRAM | Gopiballavpur-I,Sankrail | Jhargram Division | NOAGOAN AND ADJOINING MOUJAS PWSS | SM/12526 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 957/JHD | 22/06/2023 | 22/06/2023 | Resource Division | 29.05 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur-I,Sankrail | Jhargram Mechanical Division | NOAGOAN AND ADJOINING MOUJAS PWSS | SM/12526 | New | New Service Connection charges. |  |  | BILL/00650/2023-2024 | 31/JMD | 31/10/2023 | 31/10/2023 | WBSEDCL | 3.37 | 0 | 0 | 0
6 | JHARGRAM | Gopiballavpur-I,Sankrail | Jhargram Mechanical Division | NOAGOAN AND ADJOINING MOUJAS PWSS | SM/12526 | New | New Service connection |  |  | BILL/00658/2023-2024 | 9/JMD | 10/11/2023 | 10/11/2023 | WBSEDCL | 4.03 | 0 | 0 | 0
7 | JHARGRAM | Gopiballavpur-I,Sankrail | Jhargram Division | NOAGOAN AND ADJOINING MOUJAS PWSS | SM/12526 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of NOAGAON and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000492/2023-2024 | 168/GPSD | 05/03/2024 | 04/04/2024 | PASCHIMANCHAL ADIBASI ENGINEERS CO-OPERATIVE SOCIETY LIMITED. | 4.26 | 3.59 | 84.21 | 100
8 | JHARGRAM | Gopiballavpur-I,Sankrail | Jhargram Division | NOAGOAN AND ADJOINING MOUJAS PWSS | SM/12526 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Ragra, Rohini GP at Sankrail Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000240/2024-2025 | 653/GPSD | 19/11/2024 | 29/11/2024 | PRINT PREVIEW | 0.92 | 0.83 | 89.83 | 100
9 | JHARGRAM | Gopiballavpur-I,Sankrail | Jhargram Division | NOAGOAN AND ADJOINING MOUJAS PWSS | SM/12526 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection for Noagoan and its adjoining mouzas Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000024/2024-2025 | 501/GPSD | 30/07/2024 | 09/08/2024 | GOBINDA MAITY | 3.85 | 0 | 0 | 100
Total | [13 empty] | 23293.78 | 372.31 | 1.6