## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | PATHARNALA AND ADJOINING MOUJAS PWSS | SM/12527 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 1603/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 37.39 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Mechanical Division | PATHARNALA AND ADJOINING MOUJAS PWSS | SM/12527 | New | New service connection |  |  | BILL/00391/2023-2024 | 29/AUG | 29/08/2023 | 29/08/2023 | WBSEDCL | 3.49 | 0 | 0 | 0
3 | JHARGRAM | Jhargram | Jhargram Mechanical Division | PATHARNALA AND ADJOINING MOUJAS PWSS | SM/12527 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Pathar Nala & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000044/2023-2024 | 1247/JMD | 26/05/2023 | 22/11/2023 | DEY ENTERPRISE | 21.88 | 16.49 | 75.34 | 55
4 | JHARGRAM | Jhargram | Jhargram Division | PATHARNALA AND ADJOINING MOUJAS PWSS | SM/12527 | New | Construction of boundary wall and Allied works At Chakua, Uransol, Patharnala 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000096/2024-2025 | 1281/JHD | 03/09/2024 | 03/10/2024 | SUNIL DULE | 37.46 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Division | PATHARNALA AND ADJOINING MOUJAS PWSS | SM/12527 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation , Accommodate FHTC ( 1700 nos) under JJM with allied work including 02 (Two) Years Operation & Maintenance for PATHARNALA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000222/2022-2023 | 371/JHD | 14/03/2023 | 01/04/2025 | SUNIL DULE | 485.06 | 298.06 | 61.45 | 75
Total | [13 empty] | 585.28 | 314.54 | 53.74