## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni | Jhargram Division | PARSHULI AND ADJOINING MOUJAS PWSS | SM/12531 | New | Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpir-I_2_1_C under Jhargram Division in the District of Jhargram. | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000067/2022-2023 | 346/JHD | 28/09/2022 | 26/01/2023 | BISHNU PADA NANDI | 22.38 | 0 | 0 | 1
2 | JHARGRAM | Jamboni | Jhargram Division | PARSHULI AND ADJOINING MOUJAS PWSS | SM/12531 | New | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 1533/jhd | 06/09/2023 | 06/09/2023 | Resource Division | 27.63 | 0 | 0 | 0
3 | JHARGRAM | Jamboni | Jhargram Mechanical Division | PARSHULI AND ADJOINING MOUJAS PWSS | SM/12531 | New | New Service connection |  |  | BILL/00430/2023-2024 | 11/JMD | 28/09/2023 | 28/09/2023 | WBSEDCL | 2.96 | 0 | 0 | 0
4 | JHARGRAM | Jamboni | Jhargram Mechanical Division | PARSHULI AND ADJOINING MOUJAS PWSS | SM/12531 | New | New Service connection |  |  | BILL/00431/2023-2024 | 12/JMD | 28/09/2023 | 28/09/2023 | WBSEDCL | 4.71 | 0 | 0 | 0
5 | JHARGRAM | Jamboni | Jhargram Division | PARSHULI AND ADJOINING MOUJAS PWSS | SM/12531 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line,Installation of display Board, soil investigation ,including 02(Two) Years Operation & Maintenance & Accommodate FHTC (1226 nos) under JJM with allied work for Parshuli PWSS in Jamboni Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHEDte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-III | ORD/000216/2022-2023 | 346/JHD | 10/03/2023 | 03/03/2025 | ASIS KUMAR SARANGI | 337.12 | 253.65 | 75.24 | 90
6 | JHARGRAM | Jamboni | Jhargram Division | PARSHULI AND ADJOINING MOUJAS PWSS | SM/12531 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Parshuli and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division | ORD/000584/2023-2024 | 521/JRWS | 15/03/2024 | 14/05/2024 | TAPAS KUMAR JANA | 4.58 | 0 | 0 | 0
7 | JHARGRAM | Jamboni | Jhargram Mechanical Division | PARSHULI AND ADJOINING MOUJAS PWSS | SM/12531 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Par Shuli & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000207/2023-2024 | 2268/JMD | 09/08/2023 | 03/08/2024 | JIBON GHOSH | 22.53 | 18.95 | 84.1 | 80
8 | JHARGRAM | Jamboni | Jhargram Division | PARSHULI AND ADJOINING MOUJAS PWSS | SM/12531 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Kenddangri GP at Jambani Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-III | ORD/000249/2024-2025 | 371/JRWS | 04/10/2024 | 14/10/2024 | GOPAL JANA | 0.75 | 0 | 0 | 100
Total | [13 empty] | 422.66 | 272.6 | 64.5