## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DAHATMAL AND IT'S ADJOINING MOUJAS PWSS | SM/12532 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dahatmal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000034/2023-2024 | 1232/JMD | 26/05/2023 | 22/11/2024 | M/S. NABIN GOPAL SENGUPTA | 20.79 | 0 | 0 | 75
2 | JHARGRAM | Jhargram | Jhargram Division | DAHATMAL AND IT'S ADJOINING MOUJAS PWSS | SM/12532 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 53.11 | 0.43 | 25
3 | JHARGRAM | Jhargram | Jhargram Division | DAHATMAL AND IT'S ADJOINING MOUJAS PWSS | SM/12532 | New | Construction of boundary wall and Allied works At Dahatmal,Bagmuri,Champasol 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000097/2024-2025 | 1280/JHD | 03/09/2024 | 03/10/2024 | PROVAT KUMAR DE | 37.25 | 0 | 0 | 30
4 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DAHATMAL AND IT'S ADJOINING MOUJAS PWSS | SM/12532 | New | new service connection charges at Dahatmul-II water supply scheme |  |  | BILL/01473/2024-2025 | 437/JMD | 05/12/2024 | 05/12/2024 | WBSEDCL | 3.01 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DAHATMAL AND IT'S ADJOINING MOUJAS PWSS | SM/12532 | New | new service connection charges at Dahatmul-I water supply scheme |  |  | BILL/01472/2024-2025 | 436/JMD | 05/12/2024 | 05/12/2024 | WBSEDCL | 9.37 | 0 | 0 | 0
Total | [13 empty] | 12355.18 | 53.11 | 0.43