## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni | Central Drilling | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Laying of Distribution pipe line, Accommodate FHTC ( 420 nos) under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000120/2023-2024 | 1313/JHD | 09/08/2023 | 07/11/2023 | NIRMAL DUTTA | 31.88 | 0 | 0 | 0
3 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Sinking of Tube Well, Laying of Distribution pipe line under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000144/2023-2024 | 1335/JHD | 10/08/2023 | 09/10/2023 | NRIPENDRA NATH SINGHA | 19.55 | 0 | 0 | 0
4 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Laying distribution pipe line under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000145/2023-2024 | 1319/JHD | 10/08/2023 | 08/11/2023 | RAHIBUDDIN MONDAL | 26.7 | 0 | 0 | 0
5 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Constructions of Pump House under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000146/2023-2024 | 1336/JHD | 10/08/2023 | 08/11/2023 | NRIPENDRA NATH SINGHA | 21.92 | 0 | 0 | 0
6 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Laying distribution pipe line under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000147/2023-2024 | 1337/JHD | 10/08/2023 | 08/11/2023 | NIRMAL DUTTA | 27.48 | 0 | 0 | 0
7 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Constructions of Pump House, Laying of Distribution pipe line under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000207/2023-2024 | 1613/JHD | 08/09/2023 | 07/12/2023 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.72 | 0 | 0 | 0
8 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Constructions of 400 cum OHR, Rising main pipe line, Interconnection pipe line, Installation of display Board, soil investigation, Accommodate FHTC (420 nos) under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-15) | Assistant Engineer | Junior Engineer-I | ORD/000367/2023-2024 | 2019/JHD | 04/12/2023 | 29/09/2024 | SUBHANKAR BANERJEE | 214.16 | 0 | 0 | 0
9 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Laying of Distribution pipe, Accommodate FHTC ( 420 nos) under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000363/2023-2024 | 2003/JHD | 01/12/2023 | 15/07/2025 | MAHARAJA CONSTRUCTION CO. | 46.39 | 0 | 0 | 0
10 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Laying of Distribution pipe line, Accommodate FHTC ( 420 nos) under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000361/2023-2024 | 2002/JHD | 01/12/2023 | 29/02/2024 | GOUTAM PARIA | 37.53 | 0 | 0 | 0
11 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1590/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 52.34 | 0 | 0 | 0
12 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Sinking of Tube Well, Laying of Distribution pipe line under JJM with allied work for JIRAPARA AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref: 1st Call eNIT_35 of 2022-23, SL No.-17) | Assistant Engineer | Junior Engineer-I | ORD/000451/2023-2024 | 245/JHD | 16/02/2024 | 16/04/2024 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.21 | 0 | 0 | 0
13 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Jirapara and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | Assistant Engineer | Junior Engineer-I,Junior Engineer-III | ORD/000588/2023-2024 | 527/JRWS | 16/03/2024 | 15/05/2024 | NIPENDRANATH SINGHA | 4.83 | 0 | 0 | 0
14 | JHARGRAM | Jamboni | Jhargram Division | JIRAPARA AND ADJOINING MOUJAS PWSS | SM/12533 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Chichra GP at Jambani Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-III | ORD/000242/2024-2025 | 335/JRWS | 19/09/2024 | 29/09/2024 | PRINT PREVIEW | 0.5 | 0 | 0 | 100
Total | [13 empty] | 21878.96 | 0 | 0