## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-I | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS | SM/12534 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Mahulboni and its adjoining mouzas Pipe Water Supply Scheme within Gopibalavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-III | ORD/000558/2023-2024 | 194/GPSD | 11/03/2024 | 10/04/2024 | MMS CONSTRUCTIONS PVT.LTD. | 4.24 | 4.24 | 99.98 | 100
2 | JHARGRAM | Gopiballavpur-I | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS | SM/12534 | New | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 423/JHD | 13/03/2024 | 13/03/2024 | Resource Division | 47.81 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | MAHULBANI AND ADJOINING MOUJAS PWSS | SM/12534 | New | Qutation for new service connection at MAHULBONI TW-II water supply scheme. |  |  | BILL/00169/2024-2025 | 96/JMD | 08/05/2024 | 08/05/2024 | WBSEDCL | 10.75 | 0 | 0 | 0
4 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | MAHULBANI AND ADJOINING MOUJAS PWSS | SM/12534 | New | Quotation for Mahulboni T/W - I water supply scheme. |  |  | BILL/01423/2023-2024 | 72/JMD | 15/03/2024 | 15/03/2024 | WBSEDCL | 4.3 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur-I | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS | SM/12534 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 384.87 | 3.13 | 25
6 | JHARGRAM | Gopiballavpur-I | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS | SM/12534 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Kharikamathani GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000231/2024-2025 | 644/GPSD | 19/11/2024 | 29/11/2024 | PRINT PREVIEW | 0.67 | 0.66 | 98.81 | 100
7 | JHARGRAM | Gopiballavpur-I | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS | SM/12534 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Malam GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000232/2024-2025 | 645/GPSD | 19/11/2024 | 29/11/2024 | GOPAL JANA | 0.92 | 0.91 | 98.81 | 100
8 | JHARGRAM | Gopiballavpur-I | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS | SM/12534 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Nayagram GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000233/2024-2025 | 646/GPSD | 19/11/2024 | 29/11/2024 | MANOJ KUMAR MAHATA | 0.84 | 0.83 | 98.81 | 100
9 | JHARGRAM | Gopiballavpur-I | Jhargram Division | MAHULBANI AND ADJOINING MOUJAS PWSS | SM/12534 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Arrah GP at Nayagram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000221/2024-2025 | 639/GPSD | 19/11/2024 | 29/11/2024 | PRINT PREVIEW | 0.92 | 0.91 | 98.82 | 100
Total | [13 empty] | 12355.22 | 392.42 | 3.18