## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni | Jhargram Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS | SM/12535 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 1300/JHD | 08/08/2023 | 08/08/2023 | Resource Division | 68.87 | 0 | 0 | 0
2 | JHARGRAM | Jamboni | Jhargram Mechanical Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS | SM/12535 | New | New Service connection |  |  | BILL/00432/2023-2024 | 13/JMD | 28/09/2023 | 28/09/2023 | WBSEDCL | 5.08 | 0 | 0 | 0
3 | JHARGRAM | Jamboni | Jhargram Mechanical Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS | SM/12535 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uttar Barashol & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000208/2023-2024 | 2269/JMD | 09/08/2023 | 05/02/2024 | M/S B.M. ELECTRICAL | 22.53 | 0 | 0 | 80
4 | JHARGRAM | Jamboni | Jhargram Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS | SM/12535 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection for Uttar Barsol and its adjoining mouzas Water Supply Scheme within Jamboni Block under Jhargram RWS Sub Division of Jhargram Division, P.H.E.Dte | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-III | ORD/000224/2024-2025 | 545/JRWS | 30/12/2024 | 14/01/2025 | SUNIL DULE | 2.95 | 0 | 0 | 0
5 | JHARGRAM | Jamboni | Jhargram Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS | SM/12535 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation , Accommodate FHTC ( 1191 nos) under JJM with allied work including 02 (Two) Years Operation & Maintenance for UTTAR BARASHOL AND IT'S ADJOINING MOUJAS PWSS in JAMBONI Block including supply of all labour & materials within Jhargram Sub- Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000223/2022-2023 | 372/JHD | 14/03/2023 | 13/01/2025 | SUNIL DULE | 466.4 | 0 | 0 | 90
6 | JHARGRAM | Jamboni | Jhargram Division | UTTAR BARASHOL AND ADJOINING MOUJAS PWSS | SM/12535 | New | Construction of Boundary Wall & allied works at 2nd Tube well site of Uttar Barsole and its adjoining mouzas pipe water supply Scheme within Jamboni Block under Jhargram RWS Sub Division within Jhargram Division. P.H.E. Dt (Total length 50 mtr, column size 250x250mm, M c/c ht. - 2.300 mtr from G.L.) | Assistant Engineer | The Junior Engineer-IV Jhargram Sub-Division,Junior Engineer-III | ORD/000580/2023-2024 | 515/JRWS | 15/03/2024 | 14/05/2024 | SUNIL DULE | 4.84 | 0 | 0 | 90
Total | [13 empty] | 570.67 | 0 | 0