## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jamboni | Jhargram Division | PALASHBANI AND ADJOINING MOUJAS PWSS | SM/12711 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1495/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 19.45 | 0 | 0 | 0
2 | JHARGRAM | Jamboni | Jhargram Mechanical Division | PALASHBANI AND ADJOINING MOUJAS PWSS | SM/12711 | New | New Service connection |  |  | BILL/00664/2023-2024 | 13/JMD | 10/11/2023 | 10/11/2023 | WBSEDCL | 8.33 | 0 | 0 | 0
3 | JHARGRAM | Jamboni | Jhargram Mechanical Division | PALASHBANI AND ADJOINING MOUJAS PWSS | SM/12711 | New | New Service connection |  |  | BILL/00675/2023-2024 | 22/JMD | 20/11/2023 | 20/11/2023 | WBSEDCL | 2.64 | 0 | 0 | 0
4 | JHARGRAM | Jamboni | Jhargram Mechanical Division | PALASHBANI AND ADJOINING MOUJAS PWSS | SM/12711 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Palasbani & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000206/2023-2024 | 2267/JMD | 09/08/2023 | 05/02/2024 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 22.55 | 20.18 | 89.5 | 85
5 | JHARGRAM | Jamboni | Jhargram Division | PALASHBANI AND ADJOINING MOUJAS PWSS | SM/12711 | New | Installation of display board for JJM works at different piped water supply scheme within Jamboni Block and Others Block under Jhargram Division, PHE dte. (3rd Phase) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000735/2023-2024 | 239/GPSD | 12/03/2024 | 22/03/2024 | KARNAJORA AGNIBINA SEVA SAMITY | 0.97 | 0 | 0 | 100
6 | JHARGRAM | Jamboni | Jhargram Division | PALASHBANI AND ADJOINING MOUJAS PWSS | SM/12711 | New | Sinking of Tube Well , Pump House , 100 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation ,including 02(Two) Years Operation & Maintenance & Accommodate FHTC (841 nos) under JJM with allied work for Palashbani PWSS in Jamboni Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. . | Assistant Engineer | Junior Engineer-II | ORD/000206/2022-2023 | 240/JHD | 17/02/2023 | 01/04/2025 | SUNIL DULE | 353.65 | 237.82 | 67.25 | 90
Total | [13 empty] | 407.57 | 258 | 63.3