## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1539/JHD | 06/09/2023 | 06/09/2023 | Resource Division | 60.72 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | Quotation for new service connection atRaghunathpur water supply scheme T/W -1 |  |  | BILL/00027/2024-2025 | 26/JMD | 22/04/2024 | 22/04/2024 | WBSEDCL | 3.06 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | New service connection charges for Belatikri, t/w no.-II |  |  | BILL/01391/2023-2024 | 54/JMD | 12/03/2024 | 12/03/2024 | WBSEDCL | 3.34 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I | Central Drilling | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | JHARGRAM | Binpur-I | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (24693) including 02(Two) Years Operation & Maintenance For 14 Nos Pipe water supply Scheme within BINPUR-I Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000069/2023-2024 | 1113/JHD | 18/07/2023 | 27/03/2026 | M/S SWACH ENVIRONMENT PRIVATE LTD. | 7215.68 | 0 | 0 | 55
6 | JHARGRAM | Binpur-I | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | Laying Distribution pipe line (140 mm) at Raghunathpur PWSS within Binpur-I Block under Jhargram Sub Division under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000323/2024-2025 | 416/JHD | 25/02/2025 | 26/05/2025 | ENVOTECH INFRA SOLUTION | 21.29 | 0 | 0 | 0
7 | JHARGRAM | Binpur-I | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Ramgarh GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer, Jhargram Sub-Division | ORD/000417/2024-2025 | 996/JSD | 23/10/2024 | 02/11/2024 | PRINT PREVIEW | 0.75 | 0 | 0 | 0
8 | JHARGRAM | Binpur-I | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Sijua GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer, Jhargram Sub-Division | ORD/000418/2024-2025 | 997/JSD | 23/10/2024 | 02/11/2024 | MANOJ KUMAR MAHATA | 0.92 | 0 | 0 | 0
Total | [13 empty] | 28645.51 | 0 | 0