## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1539/JHD | 06/09/2023 | 06/09/2023 | Resource Division | 60.72 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | Quotation for new service connection atRaghunathpur water supply scheme T/W -1 |  |  | BILL/00027/2024-2025 | 26/JMD | 22/04/2024 | 22/04/2024 | WBSEDCL | 3.06 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | New service connection charges for Belatikri, t/w no.-II |  |  | BILL/01391/2023-2024 | 54/JMD | 12/03/2024 | 12/03/2024 | WBSEDCL | 3.34 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | Laying Distribution pipe line (140 mm) at Raghunathpur PWSS within Binpur-I Block under Jhargram Sub Division under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000323/2024-2025 | 416/JHD | 25/02/2025 | 26/05/2025 | ENVOTECH INFRA SOLUTION | 21.29 | 0 | 0 | 0
5 | JHARGRAM | Binpur-I | Jhargram Division | RAGHUNATHPUR AND ADJOING MOUJUAS PWSS | SM/12713 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Raghunathpur and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht 2.300mtr from G.L | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer, Jhargram Sub-Division | ORD/000051/2024-2025 | 767/JSD | 09/08/2024 | 08/09/2024 | ASHOK CHATTARAJ | 4.61 | 0 | 0 | 100
Total | [13 empty] | 93.01 | 0 | 0