## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 1601/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 37.58 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Mechanical Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chandri & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000047/2023-2024 | 1250/JMD | 26/05/2023 | 22/11/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.95 | 12.63 | 57.54 | 50
3 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Accommodate FHTC (2066 nos) under JJM with allied work for CHANDRI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000051/2023-2024 | 861/JHD | 08/06/2023 | 03/06/2025 | ASIS KUMAR SARANGI | 88.73 | 31.42 | 35.41 | 85
4 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Chandri and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000202/2024-2025 | 2267/JHD | 02/12/2024 | 01/01/2025 | TAPAN KUMAR MANDAL | 7.93 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 3(three) months from the date of 1st registration on daily hire rate basis for 3 (Three) months only (From 01.01.2024 to 31.03.2024) having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer(HQ), Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000642/2023-2024 | 3112/JHD | 30/12/2023 | 30/03/2024 | TAPAN KUMAR UPADHYAY | 0.51 | 1.19 | 232.93 | 100
6 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Continuation Work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for May 2024 under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000006/2024-2025 | 40/JRWS | 30/04/2024 | 31/05/2024 | JAGOMOHAN SETUA | 0.58 | 0.52 | 90.73 | 100
7 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Continuation Work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission for June 2024 under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000007/2024-2025 | 103/JRWS | 29/05/2024 | 28/06/2024 | JAGOMOHAN SETUA | 0.89 | 0.53 | 59.22 | 100
8 | JHARGRAM | Jhargram | Jhargram Mechanical Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | new service connection charges at Chandri T/W-1,water supply scheme |  |  | BILL/00102/2024-2025 | 75/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 9.35 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Mechanical Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | new service connection charges at Chandri-II water supply scheme |  |  | BILL/01029/2024-2025 | 360/JMD | 20/09/2024 | 20/09/2024 | WBSEDCL | 5.33 | 0 | 0 | 0
10 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Sinking of Tube Well , Pump House , 250 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation under JJM with allied work for CHANDRI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1st Call eNIT_20 of 2022-23 , SL No.-1 and 2nd Call eNIT_07 of 2023-24, SL No.-2 ) | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000312/2023-2024 | 1832/JHD | 27/10/2023 | 28/12/2024 | ASIS KUMAR SARANGI | 145.7 | 41.07 | 28.19 | 50
11 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Construction of boundary wall and Allied works At Chandri, Barabari, Gramohan 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000098/2024-2025 | 1282/JHD | 03/09/2024 | 01/01/2025 | ASIS KUMAR SARANGI | 37.46 | 0 | 0 | 55
12 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Construction of Pump House , Laying distribution pipe line, Boundary wall, Installation of display Board under JJM with allied work for CHANDRI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000040/2023-2024 | 863/JHD | 08/06/2023 | 07/09/2024 | ASIS KUMAR SARANGI | 82.54 | 63.89 | 77.41 | 80
13 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Laying distribution pipe line under JJM with I allied work for CHANDRI AND IT'S ADJOINING MOUJAS PWSS in I JHARGRAM Block including supply of all labour & materials within! I Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000052/2023-2024 | 862/JHD | 08/06/2023 | 07/03/2025 | ASIS KUMAR SARANGI | 71.81 | 67.09 | 93.43 | 95
14 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Construction of Laying distribution I I pipe line under JJM with allied work for CHANDRI AND I IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000053/2023-2024 | 864/JHD | 08/06/2023 | 10/03/2025 | S.B.TRADERS | 30.65 | 22.55 | 73.57 | 75
15 | JHARGRAM | Jhargram | Jhargram Division | CHANDRI AND ADJOINING MOUJAS PWSS | SM/12715 | New | Trial run for CHANDRI AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000005/2025-2026 | 734/JHD | 02/04/2025 | 02/07/2025 | ASIS KUMAR SARANGI | 1.02 | 0 | 0 | 100
Total | [13 empty] | 542.03 | 240.89 | 44.44