## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | BARABARI AND ADJOINING MOUJAS PWSS | SM/12722 | New | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 1602/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 28.74 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Division | BARABARI AND ADJOINING MOUJAS PWSS | SM/12722 | New | Supply and Delivery of DI Specials for laying of Distribution Main including interconnection for Barabari and its adjoining mouzas Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000216/2024-2025 | 2369/JHD | 09/12/2024 | 08/01/2025 | ASSOCIATED ENGINEERS & TRADERS | 3.42 | 0 | 0 | 0
3 | JHARGRAM | Jhargram | Jhargram Mechanical Division | BARABARI AND ADJOINING MOUJAS PWSS | SM/12722 | New | New service connection charges. |  |  | BILL/00780/2023-2024 | 20/JMD | 08/12/2023 | 08/12/2023 | WBSEDCL | 9.92 | 0 | 0 | 0
4 | JHARGRAM | Jhargram | Jhargram Mechanical Division | BARABARI AND ADJOINING MOUJAS PWSS | SM/12722 | New | New Service connection charges. |  |  | BILL/01361/2023-2024 | 24/JMD | 04/03/2024 | 04/03/2024 | WBSEDCL | 3 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Mechanical Division | BARABARI AND ADJOINING MOUJAS PWSS | SM/12722 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Barabari & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000033/2023-2024 | 1231/JMD | 26/05/2023 | 22/11/2023 | KAMAKHYA ENTERPRISE | 20.79 | 17.32 | 83.31 | 87
6 | JHARGRAM | Jhargram | Jhargram Division | BARABARI AND ADJOINING MOUJAS PWSS | SM/12722 | New | Sinking of Tube Well , Pump House , 100 cum OHR, & 100 cum GLR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation & Accommodate FHTC (883 nos) under JJM with allied work including 02(Two) Years Operation & Maintenanace for BARABARI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000038/2023-2024 | 851/JHD | 08/06/2023 | 01/06/2025 | ASIS KUMAR SARANGI | 408.94 | 303.57 | 74.23 | 70
7 | JHARGRAM | Jhargram | Jhargram Division | BARABARI AND ADJOINING MOUJAS PWSS | SM/12722 | New | Construction of boundary wall and Allied works At Chandri, Barabari, Gramohan 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000098/2024-2025 | 1282/JHD | 03/09/2024 | 01/01/2025 | ASIS KUMAR SARANGI | 37.46 | 0 | 0 | 55
8 | JHARGRAM | Jhargram | Jhargram Mechanical Division | BARABARI AND ADJOINING MOUJAS PWSS | SM/12722 | New | Supply delivery & Installation of actuator operated double flanged type Sluice Valve at three different locations in the delivery pipeline with other allied works at Barabari PWSS of Jhargram block of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | Assistant Engineer | JE (M) | ORD/000033/2025-2026 | 1115/JMD | 27/05/2025 | 26/07/2025 | DEBJYOTI BASU | 11.06 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Division | BARABARI AND ADJOINING MOUJAS PWSS | SM/12722 | New | Laying of Additional Distribution pipe line for BARABARI and Its Adj. Moujas Moujas PWSS in Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000358/2024-2025 | 602/JHD | 19/03/2025 | 17/06/2025 | ASSOCIATED ENGINEERS & TRADERS | 26.93 | 0 | 0 | 100
10 | JHARGRAM | Jhargram | Jhargram Division | BARABARI AND ADJOINING MOUJAS PWSS | SM/12722 | New | DI pipe laying for Distribution main for BARABARI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000111/2025-2026 | 1314/JHD | 11/06/2025 | 09/09/2025 | ASSOCIATED ENGINEERS & TRADERS | 7.63 | 0 | 0 | 100
Total | [13 empty] | 557.88 | 320.89 | 57.52