## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Construction of Laying distribution pipe line under JJM with allied work for DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000132/2023-2024 | 1318/JHD | 10/08/2023 | 08/11/2023 | SUBHANKAR BANERJEE | 63.09 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dud Kundi & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000041/2023-2024 | 1243/JMD | 26/05/2023 | 01/02/2025 | DEBJYOTI BASU | 21.76 | 0 | 0 | 50
3 | JHARGRAM | Jhargram | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Laying distribution pipe line, under JJM with allied work for DUDKUNDI AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour, materials with in Jhargram Sub Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000042/2023-2024 | 868/JHD | 08/06/2023 | 06/09/2023 | TAPAN KUMAR MANDAL | 52.9 | 0 | 0 | 50
4 | JHARGRAM | Jhargram | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Sinking of Tube Well , Pump House , 200 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line,Installation of display Board, soil investigation , under JJM with allied work for DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1st Call eNIT_25 of 2022-23 , SL No.-1 and 2nd Call eNIT_07 of 2023-24, SL No.-4 ) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000313/2023-2024 | 1833/JHD | 27/10/2023 | 24/05/2024 | A.K. SIKDAR | 135.79 | 0 | 0 | 70
5 | JHARGRAM | Jhargram | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Dudkundi and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000204/2024-2025 | 2269/JHD | 02/12/2024 | 01/01/2025 | TAPAN KUMAR MANDAL | 7.92 | 0 | 0 | 0
6 | JHARGRAM | Jhargram | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Dudkundi and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000123/2024-2025 | 1315/JHD | 05/09/2024 | 05/10/2024 | SONU SINGH | 3.75 | 0 | 0 | 0
7 | JHARGRAM | Jhargram | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Aguiboni GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000111/2024-2025 | 1837/JHD | 20/09/2024 | 30/09/2024 | PRINT PREVIEW | 0.92 | 0 | 0 | 100
8 | JHARGRAM | Jhargram | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Bundhgora GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000112/2024-2025 | 1838/JHD | 20/09/2024 | 30/09/2024 | MANOJ KUMAR MAHATA | 0.84 | 0 | 0 | 100
9 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | NEW SERVICE CONNECTION CHARGES AT DUDHKUNDI TW-II PWSS |  |  | BILL/00893/2024-2025 | 321/JMD | 28/08/2024 | 28/08/2024 | WBSEDCL | 5.26 | 0 | 0 | 0
10 | JHARGRAM | Jhargram | Jhargram Mechanical Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | NEW SERVICE CONNECTION CHARGES AT DUDHKUNDI TW-I PWSS |  |  | BILL/00892/2024-2025 | 320/JMD | 28/08/2024 | 28/08/2024 | WBSEDCL | 3.18 | 0 | 0 | 0
11 | JHARGRAM | Jhargram | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Laying distribution pipe line, under JJM with allied work for DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000047/2023-2024 | 869/JHD | 08/06/2023 | 01/03/2025 | SUNIL DULE | 47.31 | 0 | 0 | 0
12 | JHARGRAM | Jhargram | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Laying distribution pipe line, under JJM with allied work for DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000048/2023-2024 | 870/JHD | 08/06/2023 | 01/03/2025 | SUNIL DULE | 62.73 | 0 | 0 | 0
13 | JHARGRAM | Jhargram | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Accommodate FHTC ( 1326 nos) under JJM with allied work for DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II,Junior Engineer-III | ORD/000050/2023-2024 | 871/JHD | 08/06/2023 | 30/05/2025 | SUNIL DULE | 55.4 | 0 | 0 | 0
14 | JHARGRAM | Jhargram | Jhargram Division | DUDKUNDI AND IT'S ADJOINING MOUJAS PWSS | SM/12723 | New | Construction of Boundary wall and allied works at 1st. Tube well site of Dudkundi and its adjoining mouzas Pipe Water Supply Scheme within Jhargram Block under Jhargram Division, P.H.E.Dte (Total length 100 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000110/2025-2026 | 1301/JHD | 10/06/2025 | 10/07/2025 | RADHE RADHE ENTERPRISE | 7.67 | 0 | 0 | 0
Total | [13 empty] | 468.52 | 0 | 0