## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/12724 | New | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 1556/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 29.57 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/12724 | New | Qutation for new service connection at Gobindapur T/W-1 water supply scheme. |  |  | BILL/01499/2023-2024 | 91/JMD | 22/03/2024 | 22/03/2024 | WBSEDCL | 4.74 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/12724 | New | Quotation for new service connection at Gobindapur T/W -2 water supply scheme. |  |  | BILL/01498/2023-2024 | 90/JMD | 22/03/2024 | 22/03/2024 | WBSEDCL | 4.53 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/12724 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Gobindapur and its Adjoining Mouzas PWSS , Block Binpur-I, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000053/2024-2025 | 769/JSD | 09/08/2024 | 08/09/2024 | SAMIR PATRA | 4.69 | 0 | 0 | 95
Total | [13 empty] | 43.53 | 0 | 0