## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/12724 | New | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 1556/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 29.57 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/12724 | New | Qutation for new service connection at Gobindapur T/W-1 water supply scheme. |  |  | BILL/01499/2023-2024 | 91/JMD | 22/03/2024 | 22/03/2024 | WBSEDCL | 4.74 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/12724 | New | Quotation for new service connection at Gobindapur T/W -2 water supply scheme. |  |  | BILL/01498/2023-2024 | 90/JMD | 22/03/2024 | 22/03/2024 | WBSEDCL | 4.53 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I | Central Drilling | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/12724 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | JHARGRAM | Binpur-I | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/12724 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (24693) including 02(Two) Years Operation & Maintenance For 14 Nos Pipe water supply Scheme within BINPUR-I Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000069/2023-2024 | 1113/JHD | 18/07/2023 | 27/03/2026 | M/S SWACH ENVIRONMENT PRIVATE LTD. | 7215.68 | 0 | 0 | 55
Total | [13 empty] | 28594.28 | 0 | 0