## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I | Jhargram Division | NEPURA AND ADJOINING MOUJAS PWSS | SM/12776 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1546/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 30.66 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I | Jhargram Division | NEPURA AND ADJOINING MOUJAS PWSS | SM/12776 | New | Construction of Boundary wall & allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Nepura and its Adjoining Mouzas PWSS , Block: - Binpur-I, District: - Jhargram {TYPE - B} (Total length 50 mtr, column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) (2nd Call) [Ref. eNIT 20 OF AE/JSD OF 2023-2024, SL No. 10] | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000197/2024-2025 | 1087/JSD | 28/11/2024 | 28/12/2024 | M/S. PRATIMA CONSTRUCTION | 4.05 | 0 | 0 | 0
3 | JHARGRAM | Binpur-I | Jhargram Mechanical Division | NEPURA AND ADJOINING MOUJAS PWSS | SM/12776 | New | Quotation for new sevice connection at Nepura tw-I water supply scheme. |  |  | BILL/00322/2024-2025 | 141/JMD | 24/05/2024 | 24/05/2024 | WBSEDCL | 9.91 | 0 | 0 | 0
4 | JHARGRAM | Binpur-I | Central Drilling | NEPURA AND ADJOINING MOUJAS PWSS | SM/12776 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 8.03 | 0.04 | 11
5 | JHARGRAM | Binpur-I | Jhargram Division | NEPURA AND ADJOINING MOUJAS PWSS | SM/12776 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (24693) including 02(Two) Years Operation & Maintenance For 14 Nos Pipe water supply Scheme within BINPUR-I Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000069/2023-2024 | 1113/JHD | 18/07/2023 | 27/03/2026 | M/S SWACH ENVIRONMENT PRIVATE LTD. | 7215.68 | 198.16 | 2.75 | 55
6 | JHARGRAM | Binpur-I | Jhargram Division | NEPURA AND ADJOINING MOUJAS PWSS | SM/12776 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Lalgarh GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer, Jhargram Sub-Division | ORD/000415/2024-2025 | 988/JSD | 04/10/2024 | 14/10/2024 | MANOJ KUMAR MAHATA | 0.92 | 0 | 0 | 0
7 | JHARGRAM | Binpur-I | Jhargram Division | NEPURA AND ADJOINING MOUJAS PWSS | SM/12776 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Nepura GP at Binpur-I Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer, Jhargram Sub-Division | ORD/000416/2024-2025 | 989/JSD | 04/10/2024 | 14/10/2024 | GOPAL JANA | 0.92 | 0 | 0 | 0
Total | [13 empty] | 28601.9 | 206.19 | 0.72