## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Accommodate FHTC ( 1591 nos) under JJM with allied work for RADHANAGAR AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000028/2023-2024 | 858/JHD | 08/06/2023 | 06/09/2023 | SUNIL DULE | 67.72 | 33.26 | 49.12 | 90
2 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Radhanagar & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000045/2023-2024 | 1248/JMD | 26/05/2023 | 22/11/2023 | BEE GEE CONSTRUCTION | 21.86 | 17.9 | 81.9 | 100
3 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Construction of 250 cum OHR, Rising main pipe line, Laying distribution pipe line, soil investigation under JJM with allied work for RADHANAGAR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref: 1 st Call eNIT_17 of 2022-23, SL No.-1 and 2nd Call eNIT_03 of 2023-24, SL No.-1) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000294/2023-2024 | 1717/JHD | 29/09/2023 | 20/11/2025 | PARTHA PROTIM PRADHAN | 94.29 | 0 | 0 | 60
4 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Construction of Laying distribution pipe line under JJM with allied work for RADHANAGAR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000019/2023-2024 | 815/JHD | 02/06/2023 | 31/08/2023 | SUNIL DULE | 94.39 | 82.66 | 87.57 | 100
5 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Sinking of Tube Well , Interconnection pipe line, Laying distribution pipe line, under JJM with allied work for RADHANAGAR AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000014/2023-2024 | 649/JHD | 11/05/2023 | 09/08/2023 | R. CONSTRUCTION | 47.91 | 45.98 | 95.96 | 95
6 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Construction of Pump House , Laying distribution pipe line, Boundary wall, Installation of display Board under JJM with allied work for RADHANAGAR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (2nd Call Ref eNIT_17 of 2022-23 , SL No.-3 ) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000123/2023-2024 | 1322/JHD | 10/08/2023 | 08/11/2023 | R. CONSTRUCTION | 96.19 | 83.46 | 86.76 | 100
7 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 1591/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 60.65 | 0 | 0 | 0
8 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | New Service connection |  |  | BILL/00668/2023-2024 | 16/JMD | 10/11/2023 | 10/11/2023 | WBSEDCL | 6.88 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | New service connection |  |  | BILL/00389/2023-2024 | 27/AUG | 29/08/2023 | 29/08/2023 | WBSEDCL | 6.24 | 0 | 0 | 0
10 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Radhanagar and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000201/2024-2025 | 2266/JHD | 02/12/2024 | 01/01/2025 | TAPAN KUMAR MANDAL | 8.01 | 0 | 0 | 0
11 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Stagging of GI Pipe at Bindukata under Radhanagar PWSS under Jhargram Block under Jhargram District. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000461/2023-2024 | 341/JHD | 29/02/2024 | 30/03/2024 | A R CONSTRUCTION | 0.96 | 0.77 | 80.01 | 100
12 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Stagging of GI Pipe at Murgidihi, Kanyaduba under Radhanagar PWSS under Jhargram Block under Jhargram District. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000462/2023-2024 | 342/JHD | 29/02/2024 | 30/03/2024 | A R CONSTRUCTION | 0.91 | 0.72 | 80 | 100
13 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Manik-para GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000117/2024-2025 | 1843/JHD | 20/09/2024 | 30/09/2024 | MANOJ KUMAR MAHATA | 0.84 | 0.84 | 100 | 100
14 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Nedabahara GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000118/2024-2025 | 1844/JHD | 20/09/2024 | 30/09/2024 | PRINT PREVIEW | 0.92 | 0.92 | 100 | 100
15 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Patashimul, Salboni GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000119/2024-2025 | 1845/JHD | 20/09/2024 | 30/09/2024 | MANOJ KUMAR MAHATA | 0.84 | 0.84 | 100 | 100
16 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | New service connection |  |  | BILL/01766/2023-2024 | 125/JMD | 29/03/2024 | 29/03/2024 | WBSEDCL | 0.82 | 0 | 0 | 0
17 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Balance work for Laying DI Rising Main Work for Radhanagar Water Supply Scheme within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000092/2025-2026 | 1177/JHD | 27/05/2025 | 26/07/2025 | SUNIL DULE | 2.02 | 0 | 0 | 0
18 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Trial run for RADHANGAR AND ADJOINING MOUZAS PWSS scheme within Jhargram Block under Jhargram Division, PHE Dte. for 3 months. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000004/2025-2026 | 733/JHD | 02/04/2025 | 02/07/2025 | SUNIL DULE | 1.04 | 0 | 0 | 0
19 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Construction of boundary wall and Allied works At Radhanagar 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000113/2025-2026 | 1356/JHD | 16/06/2025 | 16/07/2025 | SUNIL DULE | 11.42 | 0 | 0 | 0
20 | JHARGRAM | Jhargram | Jhargram Division | RADHANAGAR AND ADJOINING MOUJAS PWSS | SM/12777 | New | Balance work for Laying Disribution Main HDPE Pipe Work for Radhanagar Water Supply Scheme within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000083/2025-2026 | 1178/JHD | 27/05/2025 | 26/07/2025 | SUNIL DULE | 4.44 | 0 | 0 | 100
Total | [13 empty] | 528.34 | 267.35 | 50.6