## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | RAJBAND AND ADJOINING MOUJAS PWSS | SM/12842 | New | Construction of boundary wall and Allied works At Burimol, Rajband, Bhaudi , Metial 1st and 2nd Tubewell site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000023/2024-2025 | 1077/JHD | 25/07/2024 | 23/03/2025 | M/S MITRA BROTHERS | 48.9 | 0 | 0 | 40
2 | JHARGRAM | Jhargram | Jhargram Division | RAJBAND AND ADJOINING MOUJAS PWSS | SM/12842 | New | Construction of Pump House , 100 cum OHR & 250 Cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Soil investigation & Accommodate FHTC (3051 nos) under JJM with allied work including 02(Two) Years Operation & Maintanance for RAJBAND, PINDRAKULI & RAJABASA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000380/2024-2025 | 667/JHD | 26/03/2025 | 22/09/2025 | ASIS KUMAR SARANGI | 813.53 | 0 | 0 | 0
Total | [13 empty] | 862.43 | 0 | 0