## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/13678 | Augmentation | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Domsole PWSS in Binpur-1I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | Junior Engineer-II | ORD/000120/2021-2022 | 153/JSD | 12/08/2021 | 26/08/2021 | RADIANT | 1.7 | 0 | 0 | 1
2 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/13678 | Augmentation | Sinking of 1 (One) No. Replacement tube Well with Augmentation & Retrofitting works for Domsole PWSS to accommodate FHTC (Phase-II) in Binpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000145/2022-2023 | 647/JHD | 01/12/2022 | 22/12/2022 | DEBASISH DOGRA | 14.91 | 0 | 0 | 100
3 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/13678 | Augmentation | Balance Work of Augmentation of Domsole Piped Water Supply Scheme within Binpur-II Block under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000348/2023-2024 | 970/JSD | 10/11/2023 | 01/12/2023 | DEBASISH DOGRA | 3.83 | 0 | 0 | 100
4 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/13678 | Augmentation | Construction of boundary wall, switch room & interconnection of T/Well for augmentation of Domsole water supply scheme with in Binpur-ii block under Jhargram division, P.H.E Dte. | Assistant Engineer | Junior Engineer-II | ORD/000180/2023-2024 | 1398/JHD | 18/08/2023 | 02/10/2023 | ASOKE KUMAR MAHATA | 8.57 | 0 | 0 | 100
5 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/13678 | Augmentation | New Service connection charges. |  |  | BILL/01157/2023-2024 | 37/JMD | 23/01/2024 | 23/01/2024 | WBSEDCL | 3 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/13678 | Augmentation | New Service Connection Charges for Domsole T/W-I PWSS |  |  | BILL/00896/2024-2025 | 324/JMD | 28/08/2024 | 28/08/2024 | WBSEDCL | 3.7 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Mechanical Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/13678 | Augmentation | New Service Connection Charges for Domsole-II PWSS |  |  | BILL/00895/2024-2025 | 323/JMD | 28/08/2024 | 28/08/2024 | WBSEDCL | 3.7 | 0 | 0 | 0
8 | JHARGRAM |  | Jhargram Division | Augmentation of Ground Water Based Domsole PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | SM/13678 | Augmentation | REPAIRING OF EXISTING F.H.T.C AT MOUZA DAMSOLE UNDER DAMSOLE W/S SCHEME WITH IN BINPUR-II BLOCK UNDER JHARGRAM DIVISION, P.H.E. DTE | Assistant Engineer | Junior Engineer-II | ORD/000184/2024-2025 | 1078/JSD | 27/11/2024 | 11/12/2024 | SUNIL DULE | 0.97 | 0 | 0 | 0
Total | [13 empty] | 40.37 | 0 | 0