## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-II,Jamboni | Jhargram Mechanical Division | KHARBANDI AND ADJOINING MOUZAS PWSS | SM/14133 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I, II & III and making compound lighting arrangement at T/W no. I of Barbaria & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000049/2023-2024 | 1253/JMD | 26/05/2023 | 22/11/2023 | SAMARPITA ENGINEERING | 31.73 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-II,Jamboni | Jhargram Division | KHARBANDI AND ADJOINING MOUZAS PWSS | SM/14133 | New | Sinking of Tube Well , Pump House , 350 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation & Accommodate FHTC ( 2994 nos) under JJM with allied work including 02(Two) Years Operation & Maintenanace for KHARBANDI AND IT'S ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-II block | ORD/000114/2023-2024 | 1218/JHD | 27/07/2023 | 23/01/2024 | SIBSANKAR CHOWDHURY | 820.21 | 157.8 | 19.24 | 10
3 | JHARGRAM | Gopiballavpur-II,Jamboni | Jhargram Division | KHARBANDI AND ADJOINING MOUZAS PWSS | SM/14133 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1558/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 229.2 | 0 | 0 | 0
Total | [13 empty] | 1081.14 | 157.8 | 14.6