## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RAJABASA AND ADJOINING MOUJAS PWSS | SM/14184 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I, II, III & IV and making compound lighting arrangement at T/W no. I of Rajabasa & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000050/2023-2024 | 1255/JMD | 26/05/2023 | 22/11/2023 | DEBJYOTI BASU | 43.9 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS | SM/14184 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Radhanagar GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000120/2024-2025 | 1846/JHD | 20/09/2024 | 30/09/2024 | PRINT PREVIEW | 0.92 | 0 | 0 | 100
3 | JHARGRAM | Jhargram | Central Drilling | RAJABASA AND ADJOINING MOUJAS PWSS | SM/14184 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Driller In Charge | Junior Engineer | ORD/000001/2024-2025 | 91/CDD | 25/04/2024 | 25/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 19.59 | 12.64 | 10
4 | JHARGRAM | Jhargram | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS | SM/14184 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Sapdhara GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000121/2024-2025 | 1847/JHD | 20/09/2024 | 30/09/2024 | GOPAL JANA | 0.84 | 0.84 | 100 | 100
5 | JHARGRAM | Jhargram | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS | SM/14184 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Sardiha GP at Jhargram Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000122/2024-2025 | 1848/JHD | 20/09/2024 | 30/09/2024 | MANOJ KUMAR MAHATA | 0.5 | 0.5 | 100 | 100
6 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RAJABASA AND ADJOINING MOUJAS PWSS | SM/14184 | New | NEW SERVICE CONNECTION CHARGES AT RAJABASA TW-II PWSS |  |  | BILL/00894/2024-2025 | 322/JMD | 28/08/2024 | 28/08/2024 | WBSEDCL | 4.04 | 0 | 0 | 0
7 | JHARGRAM | Jhargram | Jhargram Mechanical Division | RAJABASA AND ADJOINING MOUJAS PWSS | SM/14184 | New | new service connection charges at Rajabasa-I water supply scheme |  |  | BILL/01030/2024-2025 | 361/JMD | 20/09/2024 | 20/09/2024 | WBSEDCL | 3.37 | 0 | 0 | 0
8 | JHARGRAM | Jhargram | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS | SM/14184 | New | Construction of Pump House , 100 cum OHR & 250 Cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, Soil investigation & Accommodate FHTC (3051 nos) under JJM with allied work including 02(Two) Years Operation & Maintanance for RAJBAND, PINDRAKULI & RAJABASA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000380/2024-2025 | 667/JHD | 26/03/2025 | 22/09/2025 | ASIS KUMAR SARANGI | 813.53 | 0 | 0 | 0
9 | JHARGRAM | Jhargram | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS | SM/14184 | New | Laying of extention distribution pipe line for under Rajabasa PWSS in Jhargram block within Jhargram district under Jhargram division P.H.E dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000316/2024-2025 | 369/JHD | 20/02/2025 | 06/04/2025 | KOUSIK MONDAL | 4.76 | 0 | 0 | 0
10 | JHARGRAM | Jhargram | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS | SM/14184 | New | Laying of extention distribution pipe line for Manikpara under Rajabasa PWSS in Jhargram block within Jhargram district under Jhargram Division, PHE Dte. (phase- II) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000317/2024-2025 | 370/JHD | 20/02/2025 | 06/04/2025 | KOUSIK MONDAL | 4.79 | 0 | 0 | 100
11 | JHARGRAM | Jhargram | Jhargram Division | RAJABASA AND ADJOINING MOUJAS PWSS | SM/14184 | New | Laying of extension distribution pipe line for Manikpara under Rajabasa PWSS in Jhargram block within Jhargram district under Jhargram Division, PHE Dte. (phase- III) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000318/2024-2025 | 371/JHD | 20/02/2025 | 06/04/2025 | KOUSIK MONDAL | 4.76 | 0 | 0 | 100
Total | [13 empty] | 1036.42 | 20.93 | 2.02