## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-IV (MADHABPUR) AND IT'S ADJOINING MOUJAS PWSS | SM/16675 | New | Supply, delivery and installation of horizontal split casing type centrifugal pumping machineries with suitable rated horizontal foot mounted Induction motor sets and allied electro-mechanical accessories for low lift and high lift pumping operations at Dharampur Zone-IV (Madhabpur) and its adjoining moujas surface water based piped water supply scheme under Jhargram Mechanical Division, PHE Dte. in the district of Jhargram. | Assistant Engineer | JE (M) | ORD/000164/2023-2024 | 2009/JMD | 02/08/2023 | 29/01/2024 | M/S. EMMESS | 50.21 | 0 | 0 | 0
2 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-IV (MADHABPUR) AND IT'S ADJOINING MOUJAS PWSS | SM/16675 | New | Surveying, planning, designing ,delivery, erection, construction, commissioning and completion in all respect of all Civil, Electrical and Mechanical Works including all allied, related and enabling works for the proposed DHARAMPUR ZONE -IV (MADHABPUR) Piped water supply Scheme based on surface water of Open Cast Stone Mine /pond at DHARAMPUR, Block Binpur-II district of Jhargram | Assistant Engineer | Junior Engineer-II | ORD/000311/2023-2024 | 1831/JHD | 27/10/2023 | 27/03/2026 | MONDAL PRECISION PRIVATE LIMITED | 502 | 0 | 0 | 6
Total | [13 empty] | 552.21 | 0 | 0