## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Construction of District Water Testing Laboratory under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000318/2023-2024 | 1843/JHD | 31/10/2023 | 30/06/2025 | SAIKAT DANDAPAT | 45.24 | 33.36 | 73.74 | 33
2 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | Assistant Engineer | Junior Engineer-II | ORD/000123/2025-2026 | 2203/JHD | 14/10/2025 | 13/12/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 13.3 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | Assistant Engineer | Junior Engineer-II | ORD/000185/2025-2026 | 2204/JHD | 14/10/2025 | 13/12/2025 | UTSAV AGENCY | 2.36 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Engagement of 04(Four) nos. Laboratory Personnel ( One Chemist , One Bacteriologist, One Laboratory Assistant, Sampling Assistant) for regular analysis, testing and monitoring of water samples for District Laboratory of Jhargram under Jhargram Division, P.H.E. Dte. (From 01/11/2025 to 31/10/2026) | Assistant Engineer | Junior Engineer-II | ORD/000188/2025-2026 | 2208/JHD | 14/10/2025 | 14/10/2026 | GOBINDA MAITY | 5.99 | 0 | 0 | 0
5 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | Assistant Engineer | Junior Engineer-II | ORD/000186/2025-2026 | 2205/JHD | 14/10/2025 | 13/12/2025 | SCIENTIFIC VENTURES | 1 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | Assistant Engineer | Junior Engineer-II | ORD/000189/2025-2026 | 2207/JHD | 14/10/2025 | 13/12/2025 | SAKTI ENTERPRISE | 0 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | Assistant Engineer | Junior Engineer-II | ORD/000187/2025-2026 | 2206/JHD | 14/10/2025 | 13/12/2025 | LAB SOLUTION | 1.4 | 0 | 0 | 0
8 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Procurement of Chemicals & Consumbles,Glassware,Plasticware etc required of the Gopiballavpur Sub Dist. Laboratory in the District of Jhargram Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000148/2025-2026 | 597/JRWS | 06/08/2025 | 21/08/2025 | UTSAV AGENCY | 0.94 | 0 | 0 | 100
9 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Procurement of Chemicals & Plasticware etc. required of the NGO Managed Laboratory in the District of Jhargram District Under Jhargram Division P.H.E. Dte | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000145/2025-2026 | 594/JRWS | 06/08/2025 | 21/08/2025 | UTSAV AGENCY | 0.94 | 0 | 0 | 100
10 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Procurement of Chemicals & Plasticware. required of the Belpahari Sub Dist. Laboratory in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000147/2025-2026 | 596/JRWS | 06/08/2025 | 21/08/2025 | UTSAV AGENCY | 0.94 | 0 | 0 | 100
11 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Procurement of Chemicals & Consumbles,Glassware,Plasticware etc. required of the Lalgarh Sub Dist. Laboratory in the District of Jhargram Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer-II | ORD/000155/2025-2026 | 598/JRWS | 06/08/2025 | 21/08/2025 | SHREE SHYAM CHEM | 0.94 | 0 | 0 | 100
12 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Procurement of Chemicals & Plasticware. required of the Gidhni Sub Dist. Laboratory in the District of Jhargram District Under Jhargram Division P.H.E. Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000146/2025-2026 | 595/JRWS | 06/08/2025 | 21/08/2025 | UTSAV AGENCY | 0.94 | 0 | 0 | 100
13 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | new service connection charges at Jhargram Sub Division |  |  | BILL/00643/2024-2025 | BP-2024-25-308 | 17/03/2025 | 17/03/2025 | WBSEDCL | 9.24 | 0 | 0 | 0
Total | [13 empty] | 83.22 | 33.36 | 40.09