## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Construction of District Water Testing Laboratory under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000318/2023-2024 | 1843/JHD | 31/10/2023 | 30/06/2025 | SAIKAT DANDAPAT | 45.24 | 0 | 0 | 33
2 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | Assistant Engineer | Junior Engineer-II | ORD/000123/2025-2026 | 2203/JHD | 14/10/2025 | 13/12/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 13.3 | 0 | 0 | 0
3 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | Assistant Engineer | Junior Engineer-II | ORD/000185/2025-2026 | 2204/JHD | 14/10/2025 | 13/12/2025 | UTSAV AGENCY | 2.36 | 0 | 0 | 0
4 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Engagement of 04(Four) nos. Laboratory Personnel ( One Chemist , One Bacteriologist, One Laboratory Assistant, Sampling Assistant) for regular analysis, testing and monitoring of water samples for District Laboratory of Jhargram under Jhargram Division, P.H.E. Dte. (From 01/11/2025 to 31/10/2026) | Assistant Engineer | Junior Engineer-II | ORD/000188/2025-2026 | 2208/JHD | 14/10/2025 | 14/10/2026 | GOBINDA MAITY | 5.99 | 0 | 0 | 0
5 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | Assistant Engineer | Junior Engineer-II | ORD/000186/2025-2026 | 2205/JHD | 14/10/2025 | 13/12/2025 | SCIENTIFIC VENTURES | 1 | 0 | 0 | 0
6 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | Assistant Engineer | Junior Engineer-II | ORD/000189/2025-2026 | 2207/JHD | 14/10/2025 | 13/12/2025 | SAKTI ENTERPRISE | 0 | 0 | 0 | 0
7 | JHARGRAM |  | Jhargram Division | Setting up of District level Water Testing Laboratory under Jhargram Division, PHE Dte. | SM/16680 | Support-WQMSP | Supply, Delivery and installation of water testing laboratory equipment, chemicals laboratory glassware reagents for setting up District water tasting laboratory for Jhargram District related to water quality monitoring and surveillance activities under jhargram division PHE Dte. Government of West Bengal. | Assistant Engineer | Junior Engineer-II | ORD/000187/2025-2026 | 2206/JHD | 14/10/2025 | 13/12/2025 | LAB SOLUTION | 1.4 | 0 | 0 | 0
Total | [13 empty] | 69.3 | 0 | 0