## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS | SM/16934 | New | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 1584/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 38.98 | 0 | 0 | 0
2 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS | SM/16934 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Dharampur Zone-I (Amlatora) and its adjoining mouzas Pipe Water Supply Scheme within Binpur-II Block under Jhargram Sub Division within Jhargram Division, P.H.E. Dte (Total length 50 mtr, column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) . (2nd Call) [Ref. eNIT 03 OF AE/JSD OF 2024-2025, SL No. 05] | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000175/2024-2025 | 1069/JSD | 26/11/2024 | 10/01/2025 | SAIKAT JANA | 3.69 | 0 | 0 | 0
3 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS | SM/16934 | New | New Service Connection Charges for Amlatora T/W - II PWSS |  |  | BILL/01031/2024-2025 | 368/JMD | 24/09/2024 | 24/09/2024 | WBSEDCL | 6.51 | 0 | 0 | 0
4 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS | SM/16934 | New | New Service Connection Charges for Amlatora T/W-I PWSS |  |  | BILL/01020/2024-2025 | 353/JMD | 13/09/2024 | 13/09/2024 | WBSEDCL | 3.56 | 0 | 0 | 0
5 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS | SM/16934 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (2294 Nos), etc.including 02(Two) Years Operation & Maintenance For DHARAMPUR ZONE-I , DHARAMPUR ZONE-VII Pipe water supply Scheme within Binpur-II Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000107/2023-2024 | 1209/JHD | 26/07/2023 | 01/04/2025 | SUNIL DULE | 761.33 | 0 | 0 | 70
6 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS | SM/16934 | New | Supply & Delivery of CI&DI Specials for laying of Rising Main including interconnection between Tube Well and Raising Main and OHR for Dharampur (Zone-I) Amratora and its adjoining mouzas Water Supply Scheme within Binpur-I Block under Jhargram Sub Division of Jhargram Division, P.H.E.Dte. (2nd Call) [Ref: 1st Call of e-NIQ-02 of AE/JSD of 2024-2025, SL. No.-01] | Assistant Engineer, Jhargram Sub-Division | Junior Engineer, Jhargram Sub-Division | ORD/000025/2025-2026 | 366/JSD | 29/04/2025 | 13/05/2025 | SUNIL DULE | 2.13 | 0 | 0 | 0
7 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-l AMLATORA AND IT'S ADJOINING MOUJAS PWSS | SM/16934 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dharampur zone-I, Amlatora & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Driller-In-Charge | Junior Engineer | ORD/000215/2023-2024 | 2281/JMD | 10/08/2023 | 04/08/2024 | ABHIJIT BASU | 22.11 | 0 | 0 | 91
Total | [13 empty] | 838.31 | 0 | 0