## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS | SM/16982 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dharampur zone-VII, Damsole & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000218/2023-2024 | 2284/JMD | 10/08/2023 | 06/02/2024 | SUBHASIS ROY | 21.03 | 0 | 0 | 0
2 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS | SM/16982 | New | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 1588/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 29.81 | 0 | 0 | 0
3 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS | SM/16982 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection for Dharampur(Zone-VII) Santal Sirshi and its adjoining mouzas Water Supply Scheme within Binpur-II Block under Jhargram Sub Division of Jhargram Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer-II | ORD/000218/2024-2025 | 1158/JSD | 16/12/2024 | 30/12/2024 | SUNIL DULE | 1.56 | 0 | 0 | 0
4 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS | SM/16982 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (2294 Nos), etc.including 02(Two) Years Operation & Maintenance For DHARAMPUR ZONE-I , DHARAMPUR ZONE-VII Pipe water supply Scheme within Binpur-II Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000107/2023-2024 | 1209/JHD | 26/07/2023 | 01/08/2025 | SUNIL DULE | 761.33 | 50.82 | 6.67 | 70
5 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS | SM/16982 | New | Supply, delivery, installation, commissioning & trial run operation of electro-mechanical components at replacement T/W no. II of Domsol water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Driller-In-Charge | Junior Engineer | ORD/000836/2023-2024 | 1652/JMD | 08/02/2024 | 07/06/2024 | MAA BHABOTARINE ENTERPRISE | 9.42 | 7.98 | 84.71 | 100
6 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-VII DAMSOL AND IT'S ADJOINING MOUJAS PWSS | SM/16982 | New | Additional Quotation for Domsol P.H-I & II water supply scheme. |  |  | BILL/01774/2024-2025 | 515/JMD | 13/03/2025 | 13/03/2025 | WBSEDCL | 1.04 | 0 | 0 | 0
Total | [13 empty] | 824.19 | 58.8 | 7.13