## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Sankrail | Jhargram Division | ANDHARI AND ADJOINING MOUJAS PWSS | SM/16991 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1503/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 28.37 | 0 | 0 | 0
2 | JHARGRAM | Sankrail | Jhargram Mechanical Division | ANDHARI AND ADJOINING MOUJAS PWSS | SM/16991 | New | New Service connection |  |  | BILL/00699/2023-2024 | 25/JMD | 29/11/2023 | 29/11/2023 | WBSEDCL | 0.05 | 0 | 0 | 0
3 | JHARGRAM | Sankrail | Jhargram Mechanical Division | ANDHARI AND ADJOINING MOUJAS PWSS | SM/16991 | New | New service connection charges. |  |  | BILL/00263/2023-2024 | 2/JMD/AUG | 17/08/2023 | 17/08/2023 | WBSEDCL | 3.2 | 0 | 0 | 0
4 | JHARGRAM | Sankrail | Jhargram Mechanical Division | ANDHARI AND ADJOINING MOUJAS PWSS | SM/16991 | New | New Service connection |  |  | BILL/00670/2023-2024 | 18/JMD | 20/11/2023 | 20/11/2023 | WBSEDCL | 2.9 | 0 | 0 | 0
5 | JHARGRAM | Sankrail | Jhargram Mechanical Division | ANDHARI AND ADJOINING MOUJAS PWSS | SM/16991 | New | Additional Service Connection Charges for Andhari P.H - II PWSS |  |  | BILL/00440/2024-2025 | 208/JMD | 20/06/2024 | 20/06/2024 | WBSEDCL | 5.7 | 0 | 0 | 0
6 | JHARGRAM | Sankrail | Jhargram Division | ANDHARI AND ADJOINING MOUJAS PWSS | SM/16991 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (5510 Nos), etc. For ANANDAPUR, ANDARI, BHAMAL SANKRAIL, DHANSOL Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000003/2023-2024 | 567/JHD | 25/04/2023 | 28/02/2026 | GOBINDA MAITY | 1535.46 | 158.67 | 10.33 | 75
Total | [13 empty] | 1575.68 | 158.67 | 10.07