## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS | SM/16993 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dharampur zone-V, Bashajuri & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000217/2023-2024 | 2283/JMD | 10/08/2023 | 06/02/2024 | SUJOY RANJAN BHOWMICK | 21.04 | 0 | 0 | 0
2 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS | SM/16993 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1597/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 94.68 | 0 | 0 | 0
3 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS | SM/16993 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (3149 Nos), etc. including 02(Two) Years Operation & Maintenance For DHARAMPUR ZONE-V , DHARAMPUR ZONE-VI Pipe water supply Scheme within Binpur-II Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer RWS, Binpur-II Devlopment Block.,Junior Engineer-II | ORD/000157/2023-2024 | 1396/JHD | 18/08/2023 | 28/09/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 977.25 | 0 | 0 | 20
4 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS | SM/16993 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Kanke GP at Binpur-II Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer, Jhargram Sub-Division | ORD/000420/2024-2025 | 1012/JSD | 05/11/2024 | 15/11/2024 | PRINT PREVIEW | 0.84 | 0 | 0 | 0
5 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-V (BASHAJURI) AND ADJOINING MOUJAS PWSS | SM/16993 | New | Installation of Land Possesion Display Boards for JJM work at Different pipe water supply scheme under Ergoda GP at Binpur-II Block under jhargram Division PHE Dte. (Phase-I) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000419/2024-2025 | 1011/JSD | 05/11/2024 | 15/11/2024 | GOPAL JANA | 0.75 | 0 | 0 | 0
Total | [13 empty] | 1094.56 | 0 | 0