## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Kantabani Villages Having Less than 20 Household at Gopiballavpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Gopiballavpur-I block | ORD/000287/2023-2024 | 1674/JHD | 21/09/2023 | 21/10/2023 | SANTOSH GHOSH | 5.79 | 0 | 0 | 0
2 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Nandan Gerya Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000281/2023-2024 | 1667/JHD | 21/09/2023 | 21/10/2023 | M/S ANKITA CONSTRUCTION | 5.65 | 3.67 | 65.03 | 98
3 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Ranijhor, Hamirpur Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000316/2023-2024 | 1853/JHD | 31/10/2023 | 15/12/2023 | NRIPENDRA NATH SINGHA | 12.06 | 0 | 0 | 20
4 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Dakshin Sol, Tangasoli Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-I | ORD/000320/2023-2024 | 1845/JHD | 31/10/2023 | 15/12/2023 | NIRMAL DUTTA | 12.06 | 0 | 0 | 20
5 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Jaygerya Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-21) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000401/2023-2024 | 3105/JHD | 29/12/2023 | 28/01/2024 | DEBDATTA MANNA | 6.11 | 5.16 | 84.39 | 95
6 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bahara Soli Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-32) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000427/2023-2024 | 101/JHD | 18/01/2024 | 17/02/2024 | BHOWMIK CONSTRUCTION | 6.1 | 0 | 0 | 80
7 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Shiarkata Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-1) | Assistant Engineer | Junior Engineer-III | ORD/000448/2023-2024 | 173/JHD | 01/02/2024 | 02/03/2024 | MA GAYETRI NIRMAN PRIVATE LIMITED | 6.03 | 0 | 0 | 0
8 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Mayurjharna, Telighana, Bandhgora, Palashbani, Bamni, Barsol(khurd), Ukhuldoba, Chakchakli, Jamda, Kunkrakhopi, Salbant Villages Having Less than 20 Household at Binpur-II Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-10) | Assistant Engineer | Junior Engineer RWS, Binpur-II Devlopment Block. | ORD/000015/2024-2025 | 913/JHD | 08/07/2024 | 06/09/2024 | SAIKAT DANDAPAT | 60.08 | 0 | 0 | 0
9 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bodakata, Jonka Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-16) | Assistant Engineer | Junior Engineer-III | ORD/000044/2024-2025 | 1132/JHD | 06/08/2024 | 20/09/2024 | HYDRO TECH ASSOCIATES | 12.02 | 0 | 0 | 0
10 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Basantapur Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-24) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000566/2023-2024 | 434/JHD | 14/03/2024 | 13/04/2024 | M/S. R.K.TRADERS | 6.16 | 0 | 0 | 0
11 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Phul Beria Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-25) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000567/2023-2024 | 433/JHD | 14/03/2024 | 13/04/2024 | KRISHNA CHANDRA DAS | 5.88 | 0 | 0 | 0
12 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Kumar Kata, Mahulbani, Beldanga,Galasia,Kamar Bandi Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-6) | Assistant Engineer | Junior Engineer RWS, Binpur-II Devlopment Block. | ORD/000172/2024-2025 | 2189/JHD | 22/11/2024 | 21/01/2025 | TARUN MAHATA | 30.29 | 0 | 0 | 0
13 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Kismat Debi, Panisol, Shida Danga Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-33) | Assistant Engineer Headquarter | Junior Engineer, Jhargram Sub-Division | ORD/000173/2024-2025 | 2188/JHD | 22/11/2024 | 06/01/2025 | TAPAS KUMAR JANA | 17.82 | 0 | 0 | 0
14 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Rasiagerya Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000286/2023-2024 | 1675/JHD | 21/09/2023 | 21/10/2023 | ASHIS SHEE | 6.15 | 5.76 | 93.68 | 100
15 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Additional pipeline of Bankati PWSS (under Below 20 PWSS) under Dharampur GP within Binpur-I Block under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000685/2023-2024 | 191/JSD | 07/03/2024 | 14/03/2024 | SAMIR PATRA | 0.74 | 0.74 | 100 | 100
16 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Kumarkata, Jl no-824 |  |  | BILL/01046/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
17 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Ghoraghata, Jl no-577 |  |  | BILL/01048/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
18 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Gaighata Jl no-624 |  |  | BILL/01062/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
19 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. (Electricity New Connection quotation : Raisageria, Jhargram Block.) |  |  | BILL/00868/2023-2024 | BP-2023-24-468 | 15/02/2024 | 15/02/2024 | WBSEDCL | 0.04 | 0 | 0 | 0
20 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Kodadanga Jl no-846 |  |  | BILL/01056/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
21 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | WBSCDCL payment for Shiarkata new connection |  |  | BILL/00037/2024-2025 |  | 09/05/2024 | 09/05/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
22 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Karkata Jl no-672 |  |  | BILL/01063/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
23 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground water based mini piped water supply scheme to accommodate FHTC in villages having less then 20 household within Jhargram District under Jhargram Division, PHE Dte. |  |  | BILL/00467/2024-2025 | BP-2024-25-270 | 23/10/2024 | 23/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.29 | 0 | 0 | 0
24 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Choto Brindabanpur, JL no-822 |  |  | BILL/01040/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
25 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Nutandi Jl no-789,Reference ID- 204237368 |  |  | BILL/01055/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
26 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | new service connection charges at Phulberia water supply scheme |  |  | BILL/00423/2024-2025 |  | 27/09/2024 | 27/09/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
27 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Bamaldaha, JL no-809 |  |  | BILL/01041/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
28 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Kamarbandi Jl no-919 |  |  | BILL/01057/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
29 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Galasia Jl no-793 |  |  | BILL/01058/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
30 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Haringanj |  |  | BILL/01034/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
31 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Phutibaria |  |  | BILL/01039/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
32 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Bhepua Jl no-630 |  |  | BILL/01054/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
33 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New Service Connection Charges for Sagbandi PWSS |  |  | BILL/00450/2024-2025 |  | 01/10/2024 | 01/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
34 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Asanboni, JL no-573 |  |  | BILL/01042/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
35 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for sitarampur |  |  | BILL/01038/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
36 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Kamarbandi Jl no-851 |  |  | BILL/01050/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
37 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Kallokal Jl no-820 |  |  | BILL/01060/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
38 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Beldanga Jl no-848 |  |  | BILL/01059/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
39 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Sushna, JL no-684 |  |  | BILL/01043/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
40 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for chakgeriapur |  |  | BILL/01037/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
41 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New Service Connection Charges for Gunguni PWSS |  |  | BILL/00449/2024-2025 |  | 01/10/2024 | 01/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
42 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | new service connection charges at Mahulbani water supply scheme |  |  | BILL/00424/2024-2025 |  | 27/09/2024 | 27/09/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
43 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Mahulboni, Jl no-677 |  |  | BILL/01045/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
44 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | WBSCDCL payment for Benageria new connection |  |  | BILL/00038/2024-2025 | BP-2024-25-298 | 23/12/2024 | 23/12/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
45 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Keudi, Jl no-838 |  |  | BILL/01047/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
46 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Bamankata Jl no-844 |  |  | BILL/01051/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
47 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Durllabhpur Jl no-650 |  |  | BILL/01061/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
48 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New Service Connection Charges for Bhakut Khulya PWSS |  |  | BILL/00446/2024-2025 |  | 01/10/2024 | 01/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
49 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New Service Connection Charges for Chhoto Kashitoriya PWSS |  |  | BILL/00447/2024-2025 |  | 01/10/2024 | 01/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
50 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New Service Connection Charges for Kismat Debi PWSS |  |  | BILL/00448/2024-2025 |  | 01/10/2024 | 01/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
51 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | 6 nos. Bill for New service connection charges under 'Ground Water Based Mini piped water supply schemes to Accommodate FHTC in villages having less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. |  |  | BILL/00531/2024-2025 | BP-2024-25-292 | 21/11/2024 | 21/11/2024 | WBSEDCL | 0.57 | 0 | 0 | 0
52 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Chhagalpota, Jl no-660 |  |  | BILL/01044/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
53 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Jaypur Jl no-693 |  |  | BILL/01049/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
54 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Bankati Jl no-842 |  |  | BILL/01052/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
55 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Bijli |  |  | BILL/01035/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
56 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for Jankipur Jl no-827 |  |  | BILL/01053/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
57 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New connection quotation bill for sauda |  |  | BILL/01036/2023-2024 | BP-2024-25-7 | 03/10/2024 | 03/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
58 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | New Service Connection Charges for Nandan Gerya PWSS |  |  | BILL/00445/2024-2025 |  | 01/10/2024 | 01/10/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
59 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | new service connection charges at TIPASOL water supply scheme |  |  | BILL/00422/2024-2025 |  | 27/09/2024 | 27/09/2024 | WBSEDCL | 0.1 | 0 | 0 | 0
60 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bhepua, Durllabhpur, Gaighata, Karkata, Phutibaria Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000279/2023-2024 | 1654/JHD | 15/09/2023 | 14/11/2023 | ENVOTECH INFRA SOLUTION | 29.49 | 26.94 | 91.37 | 100
61 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Mahul Bani Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000288/2023-2024 | 1673/JHD | 21/09/2023 | 21/10/2023 | SANTOSH GHOSH | 6.14 | 0 | 0 | 75
62 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Elagerya, Dhunamari Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-14) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000395/2023-2024 | 3054/JHD | 20/12/2023 | 11/08/2025 | SUBHRANIL DAS | 12.03 | 0 | 0 | 40
63 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bhakut Khulya Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000407/2023-2024 | 44/JHD | 09/01/2024 | 08/02/2024 | M/S MILAN DATTA | 5.69 | 0 | 0 | 75
64 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bamaldaha Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-3) | Assistant Engineer | Junior Engineer Binpur-I block | ORD/000420/2023-2024 | 80/JHD | 16/01/2024 | 15/02/2024 | SAURABH KAR | 5.89 | 4.83 | 82.01 | 100
65 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Tipasol Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-27) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000428/2023-2024 | 99/JHD | 18/01/2024 | 17/02/2024 | GANDHI MAHATA | 6.19 | 0 | 0 | 95
66 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Jangal Khas(JL 823) Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-20) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000418/2023-2024 | 79/JHD | 16/01/2024 | 15/02/2024 | UMA PRASAD DATTA | 5.91 | 0 | 0 | 0
67 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Chhota Kashitarya Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-18) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000429/2023-2024 | 100/JHD | 18/01/2024 | 17/02/2024 | DIPAK ENTERPRISE | 6 | 0 | 0 | 75
68 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Gunguni I Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-29) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000419/2023-2024 | 81/JHD | 16/01/2024 | 15/02/2024 | SUBHAMAY DANDAPAT | 5.61 | 0 | 0 | 75
69 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Fuldihi Villages Having Less than 20 Household at Gopiballavpur-I Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-35) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000433/2023-2024 | 154/JHD | 30/01/2024 | 29/02/2024 | KALYAN ADHIKARI | 6.17 | 0 | 0 | 95
70 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Parulia, Baragupta Villages Having Less than 20 Household at jamboni Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL12) | Assistant Engineer | Junior Engineer, Jhargram Division | ORD/000431/2023-2024 | 125/JHD | 24/01/2024 | 28/03/2025 | MANDAL ENTERPRISE | 11.81 | 0 | 0 | 95
71 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Jamsol, Kendubani(chhota), Tentul Muri, Ausha Pal, Babui Chati Villages Having Less than 20 Household at Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Nayagram block | ORD/000430/2023-2024 | 124/JHD | 24/01/2024 | 18/01/2025 | BRAJENDRANATH SENAPATI | 30.42 | 0 | 0 | 30
72 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Sagbandi Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000455/2023-2024 | 336/JHD | 28/02/2024 | 29/03/2024 | A R ENTERPRISE | 6.26 | 0 | 0 | 95
73 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Barakala, Beldangri Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-11) | Assistant Engineer | Junior Engineer-III | ORD/000252/2024-2025 | 40/JHD | 07/01/2025 | 21/02/2025 | DEBJIT PATRA | 12.05 | 0 | 0 | 0
74 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Chhota Rajgram, Satpati Villages Having Less than 20 Household at Jamboni Block under Jhargram Division, PHE Dte. 3rd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-17, 2nd Call eNIT_20 of EE/JHD of 2023-24, SL No.-11) | Assistant Engineer | Junior Engineer-I | ORD/000570/2023-2024 | 436/JHD | 14/03/2024 | 28/04/2024 | TAPAS PAL | 11.96 | 9.1 | 76.12 | 80
75 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Chhahazari Fulberia Villages Having Less than 20 Household at Gopiballavpur-I Block under Jhargram Division, PHE Dte. 3rd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-34, 2nd Call eNIT_20 of EE/JHD of 2023-24, SL No.-23) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000569/2023-2024 | 438/JHD | 14/03/2024 | 13/04/2024 | S.R. ENTERPRISE | 6.23 | 0 | 0 | 80
76 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Chhota Brindabanpur, Harin Ganj, Jankipur, Kallokal, Keudi Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. 3rd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-5, 2nd Call eNIT_20 of EE/JHD of 2023-24, SL No.-3) | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block | ORD/000552/2023-2024 | 377/JHD | 05/03/2024 | 16/01/2025 | TAPAN KUMAR UPADHYAY | 29.4 | 0 | 0 | 20
77 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 12(twelve) months from the date of 1st registration on daily hire rate basis for 12 (Twelve) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer(HQ), Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-II | ORD/000602/2023-2024 | 463/JHD | 16/03/2024 | 16/03/2025 | SANJIB SARKAR | 2.07 | 4.66 | 225.07 | 25
78 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Jangalkhas Villages Having Less than 20 Household at Jhargram Block under Jhargram Division, PHE Dte. 2nd Call (1st Call eNIT_34 of EE/JHD of 2022-23, SL-19) | Assistant Engineer Headquarter | Junior Engineer Jhargram Dev. Block | ORD/000017/2024-2025 | 1038/JHD | 22/07/2024 | 21/08/2024 | KOUSIK MUKHERJEE | 5.98 | 0 | 0 | 0
79 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Bankati Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000285/2023-2024 | 1672/JHD | 21/09/2023 | 21/10/2023 | SAMIR PATRA | 5.86 | 5.52 | 94.24 | 100
80 | JHARGRAM | Binpur-I,Binpur-II,Gopiballavpur-I,Jamboni,Jhargram,Nayagram,Sankrail | Jhargram Division | Ground Water Based Mini Piped Water Supply Schemes to Accommodate FHTC in Villages Having Less than 20 Household within Jhargram District under Jhargram Division, PHE Dte. | SM/17039 | New | Schedule for Ground Water Based Stand alone Piped Water Supply Schemes to accommodate FHTC in Kamar Bandi Villages Having Less than 20 Household at Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Binpur-I block,Junior Engineer-III | ORD/000284/2023-2024 | 1666/JHD | 21/09/2023 | 21/10/2023 | SAMIR PATRA | 5.86 | 5.53 | 94.45 | 100
Total | [13 empty] | 414.76 | 71.92 | 17.34