## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Sankrail | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS | SM/17174 | New | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 955/JHD | 22/06/2023 | 22/06/2023 | Resource Division | 34.48 | 0 | 0 | 0
2 | JHARGRAM | Sankrail | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS | SM/17174 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of ROGRA and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000551/2023-2024 | 173/GPSD | 05/03/2024 | 04/04/2024 | SAUBHIK KUMAR NAG | 4.25 | 4.08 | 95.81 | 100
3 | JHARGRAM | Sankrail | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS | SM/17174 | New | Continuation work for Functional Household Tap Connection data uploading charges of different PWSS under Jhargram District in JJM_IMIS portal under Jal Jeevan Mission from 16.02.2024 to 29.02.2024 under Jhargram Division PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000695/2023-2024 | 420/JRWS | 15/02/2024 | 29/02/2024 | JAGOMOHAN SETUA | 0.53 | 0.52 | 98.2 | 100
4 | JHARGRAM | Sankrail | Jhargram Mechanical Division | RAGRA AND ADJOINING MOUJAS PWSS | SM/17174 | New | Service Connection Charges for Ragra tw-I pwss |  |  | BILL/01199/2023-2024 | 40/JMD | 01/02/2024 | 01/02/2024 | WBSEDCL | 5.66 | 0 | 0 | 0
5 | JHARGRAM | Sankrail | Jhargram Mechanical Division | RAGRA AND ADJOINING MOUJAS PWSS | SM/17174 | New | New service connection charges for Ragra w/s scheme, t/w no.II |  |  | BILL/01368/2023-2024 | 31/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 10.96 | 0 | 0 | 0
6 | JHARGRAM | Sankrail | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS | SM/17174 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House , & Providing Functional Household Tap Connection (6745 Nos), etc. For RAGRA, SATKULI CHARAR, NOAGAON, RAMPURA Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000008/2023-2024 | 607/JHD | 04/05/2023 | 01/10/2025 | GOBINDA MAITY | 1886.45 | 243.22 | 12.89 | 20
7 | JHARGRAM | Sankrail | Central Drilling | RAGRA AND ADJOINING MOUJAS PWSS | SM/17174 | New | Hiring of Diesel Driven Motor Cab (BS-III & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub-Divn-I (D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000074/2024-2025 | 33/CMSD-I | 11/02/2025 | 27/08/2025 | BINDU PRASAD DEVI | 0.94 | 0.64 | 67.99 | 0
8 | JHARGRAM | Sankrail | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS | SM/17174 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Rogra and its adjoining Mouzas, Block Sankrail, District Jhargram | Assistant Engineer | Junior Engineer-II | ORD/000020/2024-2025 | 1037/JHD | 22/07/2024 | 21/08/2024 | TAPAS PAL | 8.35 | 0 | 0 | 40
9 | JHARGRAM | Sankrail | Jhargram Division | RAGRA AND ADJOINING MOUJAS PWSS | SM/17174 | New | Supply & Delivery of DI Specials for laying of Rising Main including interconnection for Ragra and its adjoining mouzas Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division of Jhargram Division, P.H.E.Dte. | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000349/2024-2025 | 130/GPSD | 18/03/2025 | 08/04/2025 | GOBINDA MAITY | 2.15 | 0 | 0 | 100
10 | JHARGRAM | Sankrail | Central Drilling | RAGRA AND ADJOINING MOUJAS PWSS | SM/17174 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 22.76 | 0.11 | 11
Total | [13 empty] | 23293.53 | 271.21 | 1.16