## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | BHAMAL AND ADOINING MOUJAS PWSS | SM/17417 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bhamal & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000071/2023-2024 | 1242/JMD | 26/05/2023 | 22/11/2023 | M/S A.D. CONCERN | 21.75 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-II | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS | SM/17417 | New | Sinking of Tube Well, Pump House, Rising main pipe line, Interconnection pipe line, Installation of display Board, under JJM with allied work for BHAMAL AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000082/2023-2024 | 1120/JHD | 19/07/2023 | 17/10/2023 | ASIS KUMAR SARANGI | 38.26 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-II | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS | SM/17417 | New | Laying distribution pipe line, Accommodate FHTC (1009 nos) under JJM with allied work for BHAMAL AND ITS ADJOINING MOUJAS PWSS in GOPIBALLAVPUR-II Block including supply of all labour and materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000201/2023-2024 | 1517/JHD | 05/09/2023 | 03/03/2024 | SUDHAMAY MAJUMDAR | 131.09 | 0 | 0 | 0
4 | JHARGRAM | Gopiballavpur-II | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS | SM/17417 | New | Construction and commissioning of RCC Over Head Reservoir of capacity 150 cum and staging height 20 mtr. as per approved drawing with allied works of BHAMAL & its adjoining mouzas PWSS Proposed Pipe Water Supply Scheme for GOPIBALLAVPUR-II Block, District: - Jhargram. | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000380/2023-2024 | 2045/JHD | 07/12/2023 | 04/07/2024 | ABJ ENGINEERING | 71.49 | 0 | 0 | 0
5 | JHARGRAM | Gopiballavpur-II | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS | SM/17417 | New | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 1581/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 30.99 | 0 | 0 | 0
6 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | BHAMAL AND ADOINING MOUJAS PWSS | SM/17417 | New | New Service connection |  |  | BILL/00656/2023-2024 | 7/JMD | 08/11/2023 | 08/11/2023 | WBSEDCL | 2.85 | 0 | 0 | 0
7 | JHARGRAM | Gopiballavpur-II | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS | SM/17417 | New | Soil Investigation and determination of safe bearing capacity and other relevant parameters of soil for construction of Proposed O.H.R. of Gobindapur and Bhamal PWSS at Gopiballavpur-II Block under Jhargram Division, P.H.E. Dte. |  | Junior Engineer-II,Junior Engineer-III | ORD/000195/2024-2025 | 1085/JSD | 28/11/2024 | 12/12/2024 | MOYTEC | 1.34 | 0 | 0 | 0
8 | JHARGRAM | Gopiballavpur-II | Jhargram Division | BHAMAL AND ADOINING MOUJAS PWSS | SM/17417 | New | Construction of Boundary wall allied works at 2nd Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Bhamal and its Adjoining Mouzas PWSS , Block Gopiballavpur-II, District Jhargram TYPE - B Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L | Assistant Engineer | Junior Engineer, Jhargram Sub-Division | ORD/000066/2024-2025 | 791/JSD | 09/08/2024 | 08/09/2024 | S.R. ENTERPRISE | 4.79 | 0 | 0 | 0
9 | JHARGRAM | Gopiballavpur-II | Jhargram Mechanical Division | BHAMAL AND ADOINING MOUJAS PWSS | SM/17417 | New | New Service Connection Charges for Bhamal P.H -II PWSS |  |  | BILL/00428/2024-2025 | 202/JMD | 14/06/2024 | 14/06/2024 | WBSEDCL | 3.43 | 0 | 0 | 0
Total | [13 empty] | 305.98 | 0 | 0