## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 1562/JHD | 07/09/2023 | 07/09/2023 | Resource Division | 66.81 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Central Drilling | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Driller In Charge | Junior Engineer | ORD/000001/2024-2025 | 91/CDD | 25/04/2024 | 25/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 155.01 | 0 | 0 | 10
3 | JHARGRAM | Jhargram | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | NEW METER CONNECTION CHARGES AT GOBINDAPUR T/W-1 WATER SUPPLY SCHEME |  |  | BILL/00096/2024-2025 | 69/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 9.92 | 0 | 0 | 0
4 | JHARGRAM | Jhargram | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | NEW SERVICE CONNECTION CHARGES AT GOBINDAPUR T/W-2 WATER SUPPLY SCHEME |  |  | BILL/00097/2024-2025 | 70/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 4.78 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Mechanical Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gobindapur & adjoining moujas piped water supply scheme, Block-Jhargram in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000039/2023-2024 | 1236/JMD | 26/05/2023 | 01/11/2025 | DAS CONSTRUCTION | 20.78 | 0 | 0 | 50
6 | JHARGRAM | Jhargram | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | Laying distribution pipe line under JJM with allied work for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_26 of 2022-23 , SL No.-5 ) | Assistant Engineer Headquarter | Junior Engineer-I,Junior Engineer-III | ORD/000137/2023-2024 | 1341/JHD | 10/08/2023 | 08/11/2023 | RAHIBUDDIN MONDAL | 26.57 | 0 | 0 | 100
7 | JHARGRAM | Jhargram | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | Accommodate FHTC (1339 nos) under JJM with allied work for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3 rd Cali (Ref: 1st Call eNIT_26 of 2022-23, SL No.-6 and 2nd Call eNIT_08 of 2023-24, SL No.- 11) | Assistant Engineer Headquarter | Junior Engineer-I,Junior Engineer-III | ORD/000325/2023-2024 | 1858/JHD | 31/10/2023 | 29/01/2024 | M/S BLUE BIRD | 54.78 | 0 | 0 | 70
8 | JHARGRAM | Jhargram | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | Sinking of Tube Well , Pump House , 150 cum OHR, Rising main pipe line, Interconnection pipe line, Laying distribution pipe line, Installation of display Board, soil investigation under JJM with allied work for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 3rd Call (Ref 1st Call eNIT_26 of 2022-23 , SL No.-1, 2nd Call eNIT_07 of 2023-24 , SL No.-5 ) | Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division | ORD/000426/2023-2024 | 97/JHD | 18/01/2024 | 20/05/2025 | M/S SUPRIYA CHATTERJEE | 127.38 | 0 | 0 | 30
9 | JHARGRAM | Jhargram | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | Supplying and Delivery of Different dia CIDF Sluice Valve and Construction of Valve Chamber and allied works for Laying distribution of HDPE Pipe Line For Gobindapur and its Adjoining Mouzas PWSS in Jhargram Block under Jhargram Division PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000208/2024-2025 | 2296/JHD | 04/12/2024 | 03/01/2025 | TAPAN KUMAR MANDAL | 7.92 | 0 | 0 | 70
10 | JHARGRAM | Jhargram | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | Construction of boundary wall and Allied works At Gobindapur 1st and 2nd Tube well site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000095/2025-2026 | 1207/JHD | 29/05/2025 | 28/06/2025 | GRAVITA ENTERPRISE | 11.71 | 0 | 0 | 0
11 | JHARGRAM | Jhargram | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | Laying distribution pipe line under JJM with allied work for GOBINDAPUR AND ITS ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour, materials within Jhargram Sub Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer, Jhargram Division | ORD/000041/2023-2024 | 872/JHD | 08/06/2023 | 06/09/2023 | MANISHIKA CONSTRUCTION | 31.73 | 0 | 0 | 85
12 | JHARGRAM | Jhargram | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | Laying distribution pipe line under JJM with allied work for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer, Jhargram Division | ORD/000058/2023-2024 | 1089/JHD | 14/07/2023 | 12/10/2023 | LALIT BIHARI MAITY | 48.39 | 0 | 0 | 75
13 | JHARGRAM | Jhargram | Jhargram Division | GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/17571 | New | Laying distribution pipe line under JJM with allied work for GOBINDAPUR AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. 2nd Call (Ref eNIT_26 of 2022-23 , SL No.-3 ) | Assistant Engineer Headquarter | Junior Engineer-I,Junior Engineer-III | ORD/000185/2023-2024 | 1399/JHD | 18/08/2023 | 16/11/2023 | NIMAI HAZRA | 41.73 | 0 | 0 | 70
Total | [13 empty] | 607.52 | 0 | 0