## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Jhargram | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 1578/JHD | 08/09/2023 | 08/09/2023 | Resource Division | 40.51 | 0 | 0 | 0
2 | JHARGRAM | Jhargram | Jhargram Mechanical Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | New Service connection |  |  | BILL/00662/2023-2024 |  | 09/11/2023 | 09/11/2023 | WBSEDCL | 0.16 | 0 | 0 | 0
3 | JHARGRAM | Jhargram | Jhargram Mechanical Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | New service connection |  |  | BILL/00676/2023-2024 | 23/JMD | 24/11/2023 | 24/11/2023 | WBSEDCL | 1.43 | 0 | 0 | 0
4 | JHARGRAM | Jhargram | Jhargram Mechanical Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | New Service connection |  |  | BILL/00661/2023-2024 | 1/JMD | 20/11/2023 | 20/11/2023 | WBSEDCL | 5.34 | 0 | 0 | 0
5 | JHARGRAM | Jhargram | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-I) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000155/2023-2024 | 1375/JHD | 16/08/2023 | 14/11/2023 | SUJOY RANJAN BHOWMICK | 11.86 | 10.98 | 92.57 | 92
6 | JHARGRAM | Jhargram | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-L) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000181/2023-2024 | 1435/JHD | 24/08/2023 | 22/11/2023 | TAPAS KUMAR JANA | 10.64 | 9.2 | 86.47 | 82
7 | JHARGRAM | Jhargram | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-E) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000295/2023-2024 | 1719/JHD | 29/09/2023 | 28/12/2023 | AJITESH ACHARJEE | 9.35 | 8.54 | 91.33 | 95
8 | JHARGRAM | Jhargram | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-J) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000135/2023-2024 | 1320/JHD | 10/08/2023 | 08/11/2023 | HYDRO TECH ASSOCIATES | 12.1 | 11.54 | 95.37 | 77
9 | JHARGRAM | Jhargram | Jhargram Mechanical Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Saftaldiha & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | Assistant Engineer | JE (M) | ORD/000067/2023-2024 | 1237/JMD | 26/05/2023 | 22/11/2023 | MAA BHABOTARINE ENTERPRISE | 20.78 | 17.06 | 82.09 | 86
10 | JHARGRAM | Jhargram | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | Accommodate FHTC ( 499 nos) under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. (Part-1) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000138/2023-2024 | 1321/JHD | 10/08/2023 | 08/11/2023 | DHUMKETU ENGINEERING PRIVATE LIMITED | 21.08 | 18.73 | 88.87 | 95
11 | JHARGRAM | Jhargram | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | Laying distribution pipe line under JJM with allied work for SAFTALDIHA AND IT'S ADJOINING MOUJAS PWSS in JHARGRAM Block including supply of all labour & materials within Jhargram Sub-Division under Jhargram Division, PHE Dte. ( Part-A) | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000197/2023-2024 | 1565/JHD | 07/09/2023 | 06/12/2023 | M/S. SANKAR KUMAR NAG | 23.94 | 0 | 0 | 100
12 | JHARGRAM | Jhargram | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | Field Level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme In different Block in the District of Jhargram under Jhargram Division, PHE Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000747/2023-2024 | 323/JHD | 23/02/2024 | 23/05/2024 | TECHVISION | 0.6 | 0 | 0 | 95
13 | JHARGRAM | Jhargram | Jhargram Division | SAFTALDIHA AND ADJOINING MOUJAS PWSS | SM/17580 | New | Construction of boundary wall and Allied works At Saftaldiha 1st and 2nd Tube well site of public water supply schemes in Jhargram block within Jhargram District under Jhargram Division P.H.E Dte. | Assistant Engineer Headquarter | Junior Engineer-III | ORD/000094/2025-2026 | 1206/JHD | 29/05/2025 | 28/06/2025 | GRAVITA ENTERPRISE | 11.71 | 0 | 0 | 0
Total | [13 empty] | 169.5 | 76.06 | 44.87