## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Sankrail | Jhargram Division | DHANSOL AND ADJOINING MOUJAS PWSS | SM/17581 | New | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 1506/JHD | 05/09/2023 | 05/09/2023 | Resource Division | 28.78 | 0 | 0 | 0
2 | JHARGRAM | Sankrail | Jhargram Mechanical Division | DHANSOL AND ADJOINING MOUJAS PWSS | SM/17581 | New | New service connection charges |  |  | BILL/00249/2023-2024 | 12/JMD/PFMS/JUL | 27/07/2023 | 27/07/2023 | WBSEDCL | 2.83 | 0 | 0 | 0
3 | JHARGRAM | Sankrail | Jhargram Mechanical Division | DHANSOL AND ADJOINING MOUJAS PWSS | SM/17581 | New | New service connection charges |  |  | BILL/00251/2023-2024 | 14/JMD/PFMS/APR | 27/07/2023 | 27/07/2023 | WBSEDCL | 3.3 | 0 | 0 | 0
4 | JHARGRAM | Sankrail | Jhargram Mechanical Division | DHANSOL AND ADJOINING MOUJAS PWSS | SM/17581 | New | Supply, delivery, installation, commissioning & trial run of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dhansol & adjoining moujas piped water supply scheme in the district of Jhargram under Jhargram Mechanical Division, PHE. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000201/2023-2024 | 2262/JMD | 09/08/2023 | 05/02/2024 | RS ELECTROMECHANICAL CORPORATION | 21.96 | 0 | 0 | 91
5 | JHARGRAM | Sankrail | Jhargram Division | DHANSOL AND ADJOINING MOUJAS PWSS | SM/17581 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of DHANSOLA and its adjoining mouzas Pipe Water Supply Scheme within Sankrail Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junier Engineer,Gopiballavpur Sub Division | ORD/000553/2023-2024 | 174/GPSD | 05/03/2024 | 04/04/2024 | SANITARY PLANET | 4.18 | 0 | 0 | 100
6 | JHARGRAM | Sankrail | Jhargram Division | DHANSOL AND ADJOINING MOUJAS PWSS | SM/17581 | New | Sinking of Tube Well , Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system , Pump House & Providing Functional Household Tap Connection (5510 Nos), etc. For ANANDAPUR, ANDARI, BHAMAL SANKRAIL, DHANSOL Pipe water supply Scheme within Sankrail Block Under Jhargram Sub Division of Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer | Junior Engineer-II | ORD/000003/2023-2024 | 567/JHD | 25/04/2023 | 01/09/2025 | GOBINDA MAITY | 1535.46 | 0 | 0 | 75
7 | JHARGRAM | Sankrail | Jhargram Division | DHANSOL AND ADJOINING MOUJAS PWSS | SM/17581 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Dhansola and its adjoining Mouzas, Block Sankrail, District Jhargram | Assistant Engineer | Junior Engineer-II | ORD/000579/2023-2024 | 446/JHD | 14/03/2024 | 13/04/2024 | NIKHIL CHANDRA MONDAL | 8.35 | 0 | 0 | 100
Total | [13 empty] | 1604.86 | 0 | 0