## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-I | Jhargram Division | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS | SM/17584 | New | Laying of Distribution pipe line (Left-Out) for Sasrah (Z-I) & its adjoining moujas Pipe Water Supply Scheme under Gopiballavpur-I Block within Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-III | ORD/000003/2024-2025 | 878/JHD | 28/06/2024 | 28/07/2024 | MANISHIKA CONSTRUCTION | 32.4 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-I | Jhargram Division | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS | SM/17584 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Sasra( Zone-I) and its adjoining mouzas Pipe Water Supply Scheme within Gopibalavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000559/2023-2024 | 195/GPSD | 11/03/2024 | 10/04/2024 | DEBABRATA DUTTA | 4.3 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS | SM/17584 | New | NEW SERVICE CONNECTION CHARGES AT SASRA T/W-I WATER SUPPLY SCHEME |  |  | BILL/01006/2024-2025 | 346/JMD | 11/09/2024 | 11/09/2024 | WBSEDCL | 6.65 | 0 | 0 | 0
4 | JHARGRAM | Gopiballavpur-I | Jhargram Division | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS | SM/17584 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 5.88 | 0.05 | 25
5 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS | SM/17584 | New | Additional quotation for Sasra T/W-I water supply scheme |  |  | BILL/01617/2024-2025 | 468/JMD | 21/01/2025 | 21/01/2025 | WBSEDCL | 1.04 | 0 | 0 | 0
6 | JHARGRAM | Gopiballavpur-I | Central Drilling | SASARA ZONE-1 AND ADJOINING MOUJAS PWSS | SM/17584 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 9.16 | 0.04 | 11
Total | [13 empty] | 33668.92 | 15.04 | 0.04