## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Gopiballavpur-I | Jhargram Division | AMARDA AND ADJOINING MOUJAS PWSS | SM/17586 | New | Construction of Boundary wall & allied works at 2nd. Tube well site of Amarda and its adjoining mouzas Pipe Water Supply Scheme within Gopiballavpur-I Block under Gopiballavpur Sub Division within Jhargram Division, P.H.E.Dt (Total length 50 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer, Gopiballavpur Sub Division | ORD/000562/2023-2024 | 198/GPSD | 11/03/2024 | 10/04/2024 | M/S S.R. & COMPANY | 4.28 | 0 | 0 | 0
2 | JHARGRAM | Gopiballavpur-I | Jhargram Division | AMARDA AND ADJOINING MOUJAS PWSS | SM/17586 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 425/JHD | 13/03/2024 | 13/03/2024 | Resource Division | 35.66 | 0 | 0 | 0
3 | JHARGRAM | Gopiballavpur-I | Jhargram Mechanical Division | AMARDA AND ADJOINING MOUJAS PWSS | SM/17586 | New | Quotation for new service connection at Amarda T/W-I water supply scheme. |  |  | BILL/01005/2024-2025 | 347/JMD | 11/09/2024 | 11/09/2024 | WBSEDCL | 3.77 | 0 | 0 | 0
4 | JHARGRAM | Gopiballavpur-I | Central Drilling | AMARDA AND ADJOINING MOUJAS PWSS | SM/17586 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 26.28 | 0.12 | 11
5 | JHARGRAM | Gopiballavpur-I | Jhargram Division | AMARDA AND ADJOINING MOUJAS PWSS | SM/17586 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (41827 Nos), etc. For 32 nos Pipe water supply Scheme within Gopiballavpur-I, Gopiballavpur-II and JHARGRAM Block Under Jhargram Division PHE Dte. Under Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter | Junior Engineer, Gopiballavpur Sub Division,Junior Engineer-II | ORD/000298/2023-2024 | 1727/JHD | 30/09/2023 | 01/01/2025 | ADITYA ARAV DEV CONS CO. PVT. LTD. | 12284.77 | 0 | 0 | 25
6 | JHARGRAM | Gopiballavpur-I | Jhargram Division | AMARDA AND ADJOINING MOUJAS PWSS | SM/17586 | New | Construction of Boundary wall and allied works at 1st. Tube well site cum Head Work Site for Proposed Pipe Water Supply Scheme of Sumitrapur and Amarda and its adjoining Mouzas , Block Gopiballavpur-I, District Jhargram {TYPE - B} te. (Total length 125 mtr,column size 250x250mm,3.00 M c/c ht.- 2.300mtr from G.L) | Assistant Engineer | Junior Engineer-II | ORD/000326/2024-2025 | 468/JHD | 04/03/2025 | 03/05/2025 | RITESH AGARWALL | 27.15 | 0 | 0 | 0
Total | [13 empty] | 33695.38 | 26.28 | 0.08