## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | 62 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. 2nd Call (Ref: 1st Call eNIT_38 of 2022-23, SL No.-4) | Assistant Engineer | Junior Engineer-II | ORD/000315/2023-2024 | 1835/JHD | 27/10/2023 | 26/12/2023 | ASIS KUMAR SARANGI | 101.91 | 24.12 | 23.67 | 80
2 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | Four numbers (4) of yield test process need to be done at Patharchakri & Makarbhula of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000667/2023-2024 | 533/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
3 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | Four numbers (4) of yield test process need to be done at Purnapani & Chirugora of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000671/2023-2024 | 537/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
4 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | Four numbers (4) of yield test process need to be done at Shankhabhanga & Kodalbani of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000668/2023-2024 | 534/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
5 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | Four numbers (4) of yield test process need to be done at Majgerya & Birmadal of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000670/2023-2024 | 536/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
6 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | Four numbers (4) of yield test process need to be done at Jamaimari & Jantalberya of Simulpal GP of Binpur II Block, under Jhargram division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000669/2023-2024 | 535/JRWS | 16/03/2024 | 15/04/2024 | ASSOCIATED ENGINEERS & TRADERS | 0.72 | 0 | 0 | 100
7 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | New Service Connection Charges for Chirugora, Birmadal & Adjoining Moujas PWSS |  |  | BILL/00139/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
8 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | New Service Connection Charges for Shankhabhanga, Birmadal & Adjoining Moujas PWSS |  |  | BILL/00142/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
9 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | New Service Connection Charges for Purnapani, Birmadal & Adjoining Moujas PWSS |  |  | BILL/00140/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
10 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | New Service Connection Charges for Birmadal, Birmadal & Adjoining Moujas PWSS |  |  | BILL/00141/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
11 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | New Service Connection Charges for Kodalbani, Birmadal & Adjoining Moujas PWSS |  |  | BILL/00144/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
12 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | New Service Connection Charges for Patharchakri, Birmadal & Adjoining Moujas PWSS |  |  | BILL/00143/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
13 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | New Service Connection Charges for Jamaimari, Birmadal & Adjoining Moujas PWSS |  |  | BILL/00145/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
14 | JHARGRAM | Binpur-II | Jhargram Division | BIRMADAL AND ADJOINING MOUJAS PWSS | SM/17593 | New | 31 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for SIMULPAL GP (GAJPATHAR, DAKAI, BIRMADAL, BURIJHOR PWSS) under Binpur II Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000292/2023-2024 | 1714/JHD | 29/09/2023 | 29/08/2025 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 848.26 | 66.73 | 7.87 | 45
Total | [13 empty] | 955.22 | 90.85 | 9.51