## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Division | CHAKADOBA AND ADJOINING MOUJAS PWSS | SM/17596 | New | 17 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for BANASPAHARI GP ( CHAKADOBA, KHARIYARATA, KALADABAR PWSS ) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-1 ) | Assistant Engineer | Junior Engineer-II | ORD/000280/2023-2024 | 1657/JHD | 19/09/2023 | 15/07/2025 | MONDAL PRECISION PRIVATE LIMITED | 508.47 | 41.61 | 8.18 | 41
2 | JHARGRAM | Binpur-II | Jhargram Division | CHAKADOBA AND ADJOINING MOUJAS PWSS | SM/17596 | New | 34 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for BANASPAHARI GP (CHAKADOBA, KHARIYARATA,KALADABAR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_38 of 2022-23, SL No.-1) | Assistant Engineer | Junior Engineer-II | ORD/000283/2023-2024 | 1668/JHD | 21/09/2023 | 16/04/2025 | NEER UDYOG | 55.86 | 7.32 | 13.1 | 60
3 | JHARGRAM | Binpur-II | Jhargram Division | CHAKADOBA AND ADJOINING MOUJAS PWSS | SM/17596 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000840/2023-2024 | 381/JRWS | 31/01/2024 | 01/03/2024 | CARTO | 0.82 | 0 | 0 | 100
4 | JHARGRAM | Binpur-II | Jhargram Division | CHAKADOBA AND ADJOINING MOUJAS PWSS | SM/17596 | New | New Service Connection Charges for Keshmar PWSS |  |  | BILL/00120/2024-2025 |  | 13/06/2024 | 13/06/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
5 | JHARGRAM | Binpur-II | Jhargram Division | CHAKADOBA AND ADJOINING MOUJAS PWSS | SM/17596 | New | New Service Connection Charges for Neguria PWSS |  |  | BILL/00123/2024-2025 |  | 13/06/2024 | 13/06/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
6 | JHARGRAM | Binpur-II | Jhargram Division | CHAKADOBA AND ADJOINING MOUJAS PWSS | SM/17596 | New | New Service Connection Charges for Chakadoba PWSS |  |  | BILL/00125/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
7 | JHARGRAM | Binpur-II | Jhargram Division | CHAKADOBA AND ADJOINING MOUJAS PWSS | SM/17596 | New | New Service Connection Charges for Pachapani PWSS |  |  | BILL/00118/2024-2025 |  | 13/06/2024 | 13/06/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
Total | [13 empty] | 565.99 | 48.93 | 8.64