## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Division | KALADABAR AND ADJOINING MOUJAS PWSS | SM/17597 | New | 17 nos. Stand Alone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for BANASPAHARI GP ( CHAKADOBA, KHARIYARATA, KALADABAR PWSS ) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_36 of 2022-23 , SL No.-1 ) | Assistant Engineer | Junior Engineer-II | ORD/000280/2023-2024 | 1657/JHD | 19/09/2023 | 15/07/2025 | MONDAL PRECISION PRIVATE LIMITED | 508.47 | 43.71 | 8.6 | 41
2 | JHARGRAM | Binpur-II | Jhargram Division | KALADABAR AND ADJOINING MOUJAS PWSS | SM/17597 | New | 34 nos. Sinking of 125mm x 115mm x 200m Deep Tube wells by DTH method for installation of Submersible Pumping machinery for BANASPAHARI GP (CHAKADOBA, KHARIYARATA,KALADABAR PWSS) under Binpur-II Block under Jhargram Division, PHE dte. (2nd Call Ref eNIT_38 of 2022-23, SL No.-1) | Assistant Engineer | Junior Engineer-II | ORD/000283/2023-2024 | 1668/JHD | 21/09/2023 | 16/04/2025 | NEER UDYOG | 55.86 | 6.17 | 11.05 | 60
3 | JHARGRAM | Binpur-II | Jhargram Division | KALADABAR AND ADJOINING MOUJAS PWSS | SM/17597 | New | Preparation of documents for uploading in Parivesh portal for clearance of forest land proposed for PWSS under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer, Jhargram RWS Sub Division,Junior Engineer-II | ORD/000847/2023-2024 | 391/JRWS | 02/02/2024 | 03/03/2024 | MESAURE LAND | 0.82 | 0 | 0 | 100
4 | JHARGRAM | Binpur-II | Jhargram Division | KALADABAR AND ADJOINING MOUJAS PWSS | SM/17597 | New | New Service Connection Charges for Kaladabar PWSS |  |  | BILL/00127/2024-2025 | BP-2024-25-111 | 10/07/2024 | 10/07/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
5 | JHARGRAM | Binpur-II | Jhargram Division | KALADABAR AND ADJOINING MOUJAS PWSS | SM/17597 | New | New Service Connection Charges for Chourimara PWSS |  |  | BILL/00121/2024-2025 |  | 13/06/2024 | 13/06/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
6 | JHARGRAM | Binpur-II | Jhargram Division | KALADABAR AND ADJOINING MOUJAS PWSS | SM/17597 | New | New Service Connection Charges for Dharampur PWSS |  |  | BILL/00119/2024-2025 |  | 13/06/2024 | 13/06/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
Total | [13 empty] | 565.78 | 49.88 | 8.82