## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Pusda & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566), Dharampur Zone-II Barbasuli (TSM/015892)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000057/2023-2024 | 1351/JMD | 06/06/2023 | 16/07/2023 | CHAKRABORTY MINING & ENGINEERING | 21.95 | 0 | 0 | 30
2 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing additional man power & driver for Dept. rig unit with supply & delivery of UPVC consumable items with other drilling related allied works for Sinking of (125 mmX 115 mmX 200mtr) RBTW by Rotary/Combination Method at Jamirdiha & its adjacent nine (09) nos villages under Ergoda G.P. in place of (Chinbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000160/2024-2025 | 4295/JMD | 24/07/2024 | 02/09/2024 | SUBHASIS ROY | 15.61 | 0 | 0 | 0
3 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Parulia & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | JE (M) | ORD/001357/2023-2024 | 2970/JMD | 12/03/2024 | 24/03/2024 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 0 | 0 | 65
4 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Kishda & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | JE (M) | ORD/001355/2023-2024 | 2968/JMD | 12/03/2024 | 24/03/2024 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 0 | 0 | 65
5 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Additional work for Washing and development including determination of yield of Rig Bored Tube Wells at different locations in Ergoda GP under MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000084/2024-2025 | 3490/JMD | 21/06/2024 | 19/10/2024 | RSA ENTERPRISE | 6.83 | 0 | 0 | 25
6 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing additional man power & driver for Dept. rig unit with supply & delivery of UPVC consumable items with other drilling related allied works for Sinking of (125 mmX 115 mmX 200mtr) RBTW by Rotary/Combination Method at Ergoda G.P. in place of (Chinbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000148/2024-2025 | 3871/JMD | 22/07/2024 | 01/09/2025 | RSA ENTERPRISE | 8.14 | 0 | 0 | 40
7 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Siarkatia & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | JE (M) | ORD/001356/2023-2024 | 2969/JMD | 12/03/2024 | 24/03/2024 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 0 | 0 | 100
8 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of different spare parts for LMP-500 and other departmental Rig unit at MMSD(D) store under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000729/2024-2025 | 572/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.97 | 0 | 0 | 100
9 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of Mud Rotary Drilling tools at MMSD(D) store of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000733/2024-2025 | 576/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.77 | 0 | 0 | 100
10 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply and Delivery of Bucket Holder for mud pump of Halco / 238 / V-596 Rig unit under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001645/2023-2024 | 119/W/MMSD(D) | 15/03/2024 | 22/03/2024 | CHAKRABORTY MINING & ENGINEERING | 0.96 | 0 | 0 | 100
11 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of Hydraulic house and other essential spare parts at MMSD(D) store under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000730/2024-2025 | 573/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.97 | 0 | 0 | 100
12 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of essential drilling tools and Mud pump spare parts for 21D/ LT-500 and KLR/DR/DTH-500 under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000731/2024-2025 | 574/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.99 | 0 | 0 | 100
13 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply and Delivery of Piston Rod for mud pump of Halco / 238 / V-596 Rig unit under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001646/2023-2024 | 120/W/MMSD(D) | 15/03/2024 | 22/03/2024 | CHAKRABORTY MINING & ENGINEERING | 0.96 | 0 | 0 | 100
14 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of pneumatically air hammer & 165 mm dia Button Bit at MMSD (D) store for DTH drilling works under Midnapore Mechanical Sub-Division (D) in the district of Jhargram. | DIC(D)_MMSD(D) | JE (M) | ORD/000089/2024-2025 | 551/W/MMSD(D) | 21/06/2024 | 21/07/2024 | SUDIP ENGINEERING CO. | 6.06 | 0 | 0 | 100
15 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 2868/JMD | 07/03/2024 | 07/03/2024 | Resource Division | 2.16 | 0 | 0 | 0
16 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under Kanko G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/00675/2023-2024 | BP-2023-24-354 | 26/12/2023 | 26/12/2023 | SURAJ SERVICE STATION | 2.2 | 0 | 0 | 0
17 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New Service connection charges. |  |  | BILL/01345/2023-2024 | 8/JMD | 01/03/2024 | 01/03/2024 | WBSEDCL | 0.42 | 0 | 0 | 0
18 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel and lubricant for rig unit-238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Amakuli),(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division,PHE Dte |  |  | BILL/00708/2024-2025 | 273/JMD | 26/07/2024 | 26/07/2024 | SURAJ SERVICE STATION | 0.54 | 0 | 0 | 0
19 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01962/2023-2024 | 28/JMD | 26/04/2024 | 26/04/2024 | SURAJ SERVICE STATION | 1.04 | 0 | 0 | 0
20 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel and lubricant for rig unit-238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Siarkatia & Beniadihi),(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division,PHE Dte. upto 21.03.2024 |  |  | BILL/00268/2024-2025 | 126/JMD | 20/05/2024 | 20/05/2024 | SURAJ SERVICE STATION | 1.04 | 0 | 0 | 0
21 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New Service connection charges. |  |  | BILL/01139/2023-2024 | 20/JMD | 11/01/2024 | 11/01/2024 | WBSEDCL | 0.63 | 0 | 0 | 0
22 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01350/2023-2024 | 13/JMD | 01/03/2024 | 01/03/2024 | SURAJ SERVICE STATION | 1.68 | 0 | 0 | 0
23 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01773/2023-2024 | 126/JMD | 29/03/2024 | 29/03/2024 | SURAJ SERVICE STATION | 1.1 | 0 | 0 | 0
24 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel & lubricant for rig unit 238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Birgeria)(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division PHE Dte. upto 05.04.2024 |  |  | BILL/00319/2024-2025 | 133/JMD | 24/05/2024 | 24/05/2024 | SURAJ SERVICE STATION | 0.54 | 0 | 0 | 0
25 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM. Dharampur zone-II Barbasuli and adjoining moujas PWSS (SM/17924). |  |  | BILL/00675/2024-2025 | 266/JMD | 26/07/2024 | 26/07/2024 | SURAJ SERVICE STATION | 0.82 | 0 | 0 | 0
26 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New Service Connection Charges for Birgeria PWSS. DHARAMPUR ZONE-II (BARBASULI) AND ADJOINING MOUJAS PWSS |  |  | BILL/01355/2024-2025 | 419/JMD | 22/11/2024 | 22/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
27 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New Service Connection Charges for Kharipahari PWSS. DHARAMPUR ZONE-II (BARBASULI) AND ADJOINING MOUJAS PWSS |  |  | BILL/01356/2024-2025 | 420/JMD | 22/11/2024 | 22/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
28 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New service connection charge in Ratanpur, Kanko GP, Binpur-1 |  |  | BILL/01205/2023-2024 | 45/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
29 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New Service Connection Charges for Beniadihi PWSS |  |  | BILL/01357/2024-2025 | 421/JMD | 22/11/2024 | 22/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
30 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM for Scheme(SM/17924) Bibarda & Baramsol in Ergoda GP, Binpur -2 |  |  | BILL/00899/2024-2025 | 330/JMD | 29/08/2024 | 29/08/2024 | SURAJ SERVICE STATION | 1.12 | 0 | 0 | 0
31 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply, delivery of batteries for Rig unit Halco/238/V-596 under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000993/2024-2025 | 705/W/MMSD(D) | 13/12/2024 | 20/12/2024 | CHAKRABORTY MINING & ENGINEERING | 0.47 | 0 | 0 | 100
32 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ratanpur & adjacent 5 nos. villages under ¿Kanko¿ G.P. in place of {Dharampur Zone-II Barbasuli (TSM/015892)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000150/2023-2024 | 1900/JMD | 27/07/2023 | 20/01/2025 | RSA ENTERPRISE | 20.25 | 0 | 0 | 100
Total | [13 empty] | 126.22 | 0 | 0