## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Pusda & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566), Dharampur Zone-II Barbasuli (TSM/015892)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Assistant Engineer,Driller-In-Charge | JE (M),Junior Engineer | ORD/000057/2023-2024 | 1351/JMD | 06/06/2023 | 16/07/2023 | CHAKRABORTY MINING & ENGINEERING | 21.95 | 1 | 4.54 | 30
2 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing additional man power & driver for Dept. rig unit with supply & delivery of UPVC consumable items with other drilling related allied works for Sinking of (125 mmX 115 mmX 200mtr) RBTW by Rotary/Combination Method at Jamirdiha & its adjacent nine (09) nos villages under Ergoda G.P. in place of (Chinbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000160/2024-2025 | 4295/JMD | 24/07/2024 | 02/09/2024 | SUBHASIS ROY | 15.61 | 0 | 0 | 0
3 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Parulia & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | JE (M) | ORD/001357/2023-2024 | 2970/JMD | 12/03/2024 | 24/03/2024 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 3.69 | 40.77 | 65
4 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Kishda & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | JE (M) | ORD/001355/2023-2024 | 2968/JMD | 12/03/2024 | 24/03/2024 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 4.52 | 49.91 | 65
5 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Additional work for Washing and development including determination of yield of Rig Bored Tube Wells at different locations in Ergoda GP under MMSD(D) under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | Junior Engineer | ORD/000084/2024-2025 | 3490/JMD | 21/06/2024 | 19/10/2024 | RSA ENTERPRISE | 6.83 | 1.37 | 20 | 25
6 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing additional man power & driver for Dept. rig unit with supply & delivery of UPVC consumable items with other drilling related allied works for Sinking of (125 mmX 115 mmX 200mtr) RBTW by Rotary/Combination Method at Ergoda G.P. in place of (Chinbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000148/2024-2025 | 3871/JMD | 22/07/2024 | 01/09/2025 | RSA ENTERPRISE | 8.14 | 0 | 0 | 40
7 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Sinking tubewell (150 mm X 100 mm X 135 mtr) by Rotary / Combination Method with supply and delivery of UPVC consumables with drilling related works at Siarkatia & its adjacent 2 (two) nos. village under Ergoda G.P. at Binpur-II block of Jhargram District under Jhargram Mechanical Division P.H.E Dte. | Driller-In-Charge | JE (M) | ORD/001356/2023-2024 | 2969/JMD | 12/03/2024 | 24/03/2024 | CHAKRABORTY MINING & ENGINEERING | 9.06 | 4.35 | 48.01 | 100
8 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of different spare parts for LMP-500 and other departmental Rig unit at MMSD(D) store under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000729/2024-2025 | 572/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.97 | 0.97 | 100 | 100
9 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of Mud Rotary Drilling tools at MMSD(D) store of Jhargram Dist. under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000733/2024-2025 | 576/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.77 | 0.77 | 100 | 100
10 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply and Delivery of Bucket Holder for mud pump of Halco / 238 / V-596 Rig unit under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001645/2023-2024 | 119/W/MMSD(D) | 15/03/2024 | 22/03/2024 | CHAKRABORTY MINING & ENGINEERING | 0.96 | 0.96 | 100 | 100
11 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of Hydraulic house and other essential spare parts at MMSD(D) store under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000730/2024-2025 | 573/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.97 | 0.97 | 100 | 100
12 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of essential drilling tools and Mud pump spare parts for 21D/ LT-500 and KLR/DR/DTH-500 under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000731/2024-2025 | 574/W/MMSD(D) | 04/07/2024 | 11/07/2024 | B. P. TRADING CORPORATION | 0.99 | 0.99 | 100 | 100
13 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply and Delivery of Piston Rod for mud pump of Halco / 238 / V-596 Rig unit under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/001646/2023-2024 | 120/W/MMSD(D) | 15/03/2024 | 22/03/2024 | CHAKRABORTY MINING & ENGINEERING | 0.96 | 0.96 | 100 | 100
14 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply & delivery of pneumatically air hammer & 165 mm dia Button Bit at MMSD (D) store for DTH drilling works under Midnapore Mechanical Sub-Division (D) in the district of Jhargram. | DIC(D)_MMSD(D) | JE (M) | ORD/000089/2024-2025 | 551/W/MMSD(D) | 21/06/2024 | 21/07/2024 | SUDIP ENGINEERING CO. | 6.06 | 6.06 | 100 | 100
15 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 2868/JMD | 07/03/2024 | 07/03/2024 | Resource Division | 2.16 | 0 | 0 | 0
16 | JHARGRAM | Binpur-II | Jhargram Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under Kanko G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/00675/2023-2024 | BP-2023-24-354 | 26/12/2023 | 26/12/2023 | SURAJ SERVICE STATION | 2.2 | 0 | 0 | 0
17 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New Service connection charges. |  |  | BILL/01345/2023-2024 | 8/JMD | 01/03/2024 | 01/03/2024 | WBSEDCL | 0.42 | 0 | 0 | 0
18 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel and lubricant for rig unit-238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Amakuli),(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division,PHE Dte |  |  | BILL/00708/2024-2025 | 273/JMD | 26/07/2024 | 26/07/2024 | SURAJ SERVICE STATION | 0.54 | 0 | 0 | 0
19 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01962/2023-2024 | 28/JMD | 26/04/2024 | 26/04/2024 | SURAJ SERVICE STATION | 1.04 | 0 | 0 | 0
20 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel and lubricant for rig unit-238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Siarkatia & Beniadihi),(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division,PHE Dte. upto 21.03.2024 |  |  | BILL/00268/2024-2025 | 126/JMD | 20/05/2024 | 20/05/2024 | SURAJ SERVICE STATION | 1.04 | 0 | 0 | 0
21 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New Service connection charges. |  |  | BILL/01139/2023-2024 | 20/JMD | 11/01/2024 | 11/01/2024 | WBSEDCL | 0.63 | 0 | 0 | 0
22 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01350/2023-2024 | 13/JMD | 01/03/2024 | 01/03/2024 | SURAJ SERVICE STATION | 1.68 | 0 | 0 | 0
23 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Ergoda G.P. in place of {Dharampur Zone-II Barbasuli} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01773/2023-2024 | 126/JMD | 29/03/2024 | 29/03/2024 | SURAJ SERVICE STATION | 1.1 | 0 | 0 | 0
24 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Providing fuel & lubricant for rig unit 238/AR/HALCO for boring purpose under Dharampur Zone-II Barbasuli and Adjoining Mouzas PWSS(Birgeria)(SM/17924) for Binpur-II Block of Jhargram District under Jhargram Mechanical Division PHE Dte. upto 05.04.2024 |  |  | BILL/00319/2024-2025 | 133/JMD | 24/05/2024 | 24/05/2024 | SURAJ SERVICE STATION | 0.54 | 0 | 0 | 0
25 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM. Dharampur zone-II Barbasuli and adjoining moujas PWSS (SM/17924). |  |  | BILL/00675/2024-2025 | 266/JMD | 26/07/2024 | 26/07/2024 | SURAJ SERVICE STATION | 0.82 | 0 | 0 | 0
26 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New Service Connection Charges for Birgeria PWSS. DHARAMPUR ZONE-II (BARBASULI) AND ADJOINING MOUJAS PWSS |  |  | BILL/01355/2024-2025 | 419/JMD | 22/11/2024 | 22/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
27 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New Service Connection Charges for Kharipahari PWSS. DHARAMPUR ZONE-II (BARBASULI) AND ADJOINING MOUJAS PWSS |  |  | BILL/01356/2024-2025 | 420/JMD | 22/11/2024 | 22/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
28 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New service connection charge in Ratanpur, Kanko GP, Binpur-1 |  |  | BILL/01205/2023-2024 | 45/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
29 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | New Service Connection Charges for Beniadihi PWSS |  |  | BILL/01357/2024-2025 | 421/JMD | 22/11/2024 | 22/11/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
30 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM for Scheme(SM/17924) Bibarda & Baramsol in Ergoda GP, Binpur -2 |  |  | BILL/00899/2024-2025 | 330/JMD | 29/08/2024 | 29/08/2024 | SURAJ SERVICE STATION | 1.12 | 0 | 0 | 0
31 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Erection & commissioning of 30 (thirty) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Ergoda G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Dharampur Zone-II Barbasuli (TSM/015892) w/s schemes under Binpur- II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000228/2023-2024 | 2304/JMD | 14/08/2023 | 22/09/2025 | CONCORD ENGINEERING | 810.97 | 70.24 | 8.66 | 10
32 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Erection & commissioning of 23 (twenty three) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Kanko G.P. in place of (Dharampur Zone-III Kanko (TSM/015873) and Dharampur Zone-II Barbasuli (TSM/015892) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | Junior Engineer | ORD/000323/2023-2024 | 3016/JMD | 20/10/2023 | 25/08/2025 | MONDAL PRECISION PRIVATE LIMITED | 616.83 | 167.07 | 27.08 | 65
33 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-II BARBASULI AND ADJOINING MOUJAS PWSS | SM/17924 | New | Supply, delivery of batteries for Rig unit Halco/238/V-596 under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000993/2024-2025 | 705/W/MMSD(D) | 13/12/2024 | 20/12/2024 | CHAKRABORTY MINING & ENGINEERING | 0.47 | 0 | 0 | 100
Total | [13 empty] | 1533.77 | 263.91 | 17.21