## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (125 mm X 115 mm X 200 mtr) RBTW by DTH / combination method at Jamirdiha & its adjacent nine (09) nos. villages under ¿Ergoda¿ G.P. in place of {Chainbera Zone-III Joypur (TSM/015566)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000056/2023-2024 | 1350/JMD | 06/06/2023 | 16/07/2023 | SUBHASIS ROY | 22 | 6.3 | 28.62 | 30
2 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | Construction of (125 mm X 115 mm X 200 mtr.) RBTW by DTH/ combination method for providing FHTC at SITAPUR & its adjacent Seventy Three (73) nos. villages under Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000223/2023-2024 | 2297/JMD | 11/08/2023 | 06/01/2024 | MONDAL PRECISION PRIVATE LIMITED | 163.47 | 88.77 | 54.3 | 100
3 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | New Service connection |  |  | BILL/00871/2023-2024 | 44/JMD | 29/12/2023 | 29/12/2023 | WBSEDCL | 1.26 | 0 | 0 | 0
4 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | Supply of diesel and lubricants for KLR/DR/DTH-500 unit during PWSS works under JJM. |  |  | BILL/00318/2024-2025 | 134/JMD | 24/05/2024 | 24/05/2024 | SURAJ SERVICE STATION | 1.01 | 0 | 0 | 0
5 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | New Service connection charges. |  |  | BILL/01347/2023-2024 | 10/JMD | 01/03/2024 | 01/03/2024 | WBSEDCL | 0.42 | 0 | 0 | 0
6 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | New service connection charges |  |  | BILL/00852/2023-2024 | 32/JMD | 19/12/2023 | 19/12/2023 | WBSEDCL | 1.68 | 0 | 0 | 0
7 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 200 mtr.) RBTW by DTH / Combination method at Sandapara G.P. in place of (Chainbera, Zone-I Darra (SM/17930), Chainbera, Zone-II Jarda (SM/17925) and Chainbera, Zone-III Joypur (SM/18746) w/s schemes under Binpur-II Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000961/2024-2025 | 193/JMD | 30/01/2025 | 17/01/2026 | MONDAL PRECISION PRIVATE LIMITED | 58.26 | 0 | 0 | 20
8 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHAINBERA ZONE-ll JARDA AND IT'S ADJOINING MOUJAS PWSS | SM/17925 | New | Supply & delivery of filter, valve kit etc for departmental compressor unit and through maintenance at site under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000988/2024-2025 | 13/W/MMSD(D) | 13/01/2025 | 23/01/2025 | B. P. TRADING CORPORATION | 0.85 | 0 | 0 | 100
Total | [13 empty] | 248.93 | 95.06 | 38.19