## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under ¿Kanko¿ G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000022/2023-2024 | 1126/JMD | 18/05/2023 | 20/01/2025 | RSA ENTERPRISE | 27 | 23.93 | 88.64 | 85
2 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 2867/JMD | 07/03/2024 | 07/03/2024 | Resource Division | 4.8 | 0 | 0 | 0
3 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | New service connection charges for Jadabpur, Kanko GP ,Jhargram |  |  | BILL/01317/2023-2024 | 67/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
4 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Kanko G.P. in place of {Dharampur Zone-III Kanko } w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01349/2023-2024 | 12/JMD | 01/03/2024 | 01/03/2024 | SURAJ SERVICE STATION | 1.23 | 0 | 0 | 0
5 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under Kanko G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01134/2023-2024 | 17/JMD | 10/01/2024 | 10/01/2024 | SURAJ SERVICE STATION | 0.89 | 0 | 0 | 0
6 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Providing fuel & lubricant for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Mohanpur & adjacent seven (07) nos. villages under Kanko G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. |  |  | BILL/01323/2023-2024 | 91/JMD | 16/02/2024 | 16/02/2024 | SURAJ SERVICE STATION | 1.25 | 0 | 0 | 0
7 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | New service connection charge in Nachna, Kanko GP, Binpur-1 |  |  | BILL/01206/2023-2024 | 44/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
8 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | New service connection charges for Bankrasol, Kanko GP ,Jhargram |  |  | BILL/01316/2023-2024 | 67/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
9 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | New service connection charge in Salpatra, Kanko GP, Binpur-1 |  |  | BILL/01207/2023-2024 | 44/JMD | 06/02/2024 | 06/02/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
10 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | New Service connection charges. |  |  | BILL/01140/2023-2024 | 21/JMD | 11/01/2024 | 11/01/2024 | WBSEDCL | 1.47 | 0 | 0 | 0
11 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Payment for new service connection at Korkora laldanga school(H.S),Kanko under 130 PWSS scheme. |  |  | BILL/01554/2024-2025 |  | 18/12/2024 | 18/12/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
12 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Supply & delivery of upvc consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicle for Dept. Rig unit for sinking of (150 mm X 100 mm X 135 mtr) RBTW by Rotary Method at Bankrasol & adjacent eight (08) nos. villages under ¿Kanko¿ G.P. in place of {Dharampur Zone-III Kanko (TSM/015873)} w/s scheme under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000023/2023-2024 | 1127/JMD | 18/05/2023 | 18/01/2025 | RSA ENTERPRISE | 30.38 | 21.76 | 71.64 | 83
13 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Supply of necessary drilling tools for KLR/DR/DTH-500 rig unit under Jhargram Mechanical Division P.H.E Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000992/2024-2025 | 704/W/MMSD(D) | 13/12/2024 | 20/12/2024 | B. P. TRADING CORPORATION | 0.8 | 0 | 0 | 100
14 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Supply & delivery of Fast moving spare for (ELGI 450-150) departmental compressor unit under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000994/2024-2025 | 706/W/MMSD(D) | 13/12/2024 | 20/12/2024 | B. P. TRADING CORPORATION | 0.91 | 0 | 0 | 100
15 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | DHARAMPUR ZONE-lll (KANKO) AND ADJOINING MOUJAS PWSS | SM/17929 | New | Supply and Delivery of Ø 6-7/8 " Drag Bit with Tungsten Carbide insert for Mud Rotary Drilling method at MMSD(D) store in the district of Jhargram.under Jhargram Mechanical Division, P.H.E. Dte. | DIC(D)_MMSD(D) | JE (M) | ORD/000991/2024-2025 | 703/W/MMSD(D) | 13/12/2024 | 20/12/2024 | B. P. TRADING CORPORATION | 0.96 | 0 | 0 | 100
Total | [13 empty] | 70.74 | 45.69 | 64.6