## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | New | Construction of (125 mm X 115 mm X 200 mtr.) RBTW by DTH/ combination method for providing FHTC at SITAPUR & its adjacent Seventy Three (73) nos. villages under Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000223/2023-2024 | 2297/JMD | 11/08/2023 | 06/01/2024 | MONDAL PRECISION PRIVATE LIMITED | 163.47 | 0 | 0 | 100
2 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | New | New service connection charges |  |  | BILL/00851/2023-2024 | 31/JMD | 19/12/2023 | 19/12/2023 | WBSEDCL | 0.84 | 0 | 0 | 0
3 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | New | New Service connection |  |  | BILL/00870/2023-2024 | 43/JMD | 29/12/2023 | 29/12/2023 | WBSEDCL | 0.42 | 0 | 0 | 0
4 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | New | New Service connection charges. |  |  | BILL/01348/2023-2024 | 11/JMD | 01/03/2024 | 01/03/2024 | WBSEDCL | 0.63 | 0 | 0 | 0
5 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | New | Erection & commissioning of 37 (thirty seven) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000227/2023-2024 | 2303/JMD | 14/08/2023 | 31/12/2025 | CONCORD ENGINEERING | 1025.92 | 100.34 | 9.78 | 12
6 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 200 mtr.) RBTW by DTH / Combination method at Sandapara G.P. in place of (Chainbera, Zone-I Darra (SM/17930), Chainbera, Zone-II Jarda (SM/17925) and Chainbera, Zone-III Joypur (SM/18746) w/s schemes under Binpur-II Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000961/2024-2025 | 193/JMD | 30/01/2025 | 17/01/2026 | MONDAL PRECISION PRIVATE LIMITED | 58.26 | 0 | 0 | 20
Total | [13 empty] | 1249.52 | 100.34 | 8.03