## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | New | Construction of (125 mm X 115 mm X 200 mtr.) RBTW by DTH/ combination method for providing FHTC at SITAPUR & its adjacent Seventy Three (73) nos. villages under Sandapara G.P. in place of (Chainbera Zone-I Darra (TSM/015763), Chainbera Zone-II Jarda (TSM/015919) and Chainbera Zone-III Joypur (TSM/015566) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | Driller-In-Charge | Junior Engineer | ORD/000223/2023-2024 | 2297/JMD | 11/08/2023 | 06/01/2024 | MONDAL PRECISION PRIVATE LIMITED | 163.47 | 0 | 0 | 100
2 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | New | New service connection charges |  |  | BILL/00851/2023-2024 | 31/JMD | 19/12/2023 | 19/12/2023 | WBSEDCL | 0.84 | 0 | 0 | 0
3 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | New | New Service connection |  |  | BILL/00870/2023-2024 | 43/JMD | 29/12/2023 | 29/12/2023 | WBSEDCL | 0.42 | 0 | 0 | 0
4 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | New | New Service connection charges. |  |  | BILL/01348/2023-2024 | 11/JMD | 01/03/2024 | 01/03/2024 | WBSEDCL | 0.63 | 0 | 0 | 0
5 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | CHIANBERA ZONE-l DARRA AND IT'S ADJOINING MOUJAS PWSS | SM/17930 | New | Supply delivery of UPVC consumables with drilling related allied works and providing skilled & unskilled manpower & hiring supporting vehicles for Dept. Rig unit for sinking of (125 mm x 115 mm x 200 mtr.) RBTW by DTH / Combination method at Sandapara G.P. in place of (Chainbera, Zone-I Darra (SM/17930), Chainbera, Zone-II Jarda (SM/17925) and Chainbera, Zone-III Joypur (SM/18746) w/s schemes under Binpur-II Block of Jhargram Dist. under Jhargram Mechanical Division P.H.E. Dte. | Driller-In-Charge | JE (M) | ORD/000961/2024-2025 | 193/JMD | 30/01/2025 | 17/01/2026 | MONDAL PRECISION PRIVATE LIMITED | 58.26 | 0 | 0 | 20
Total | [13 empty] | 223.61 | 0 | 0