## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | JHARGRAM | Binpur-II | Bankura Mechanical | BANKSOL AND ADJOINING MOUJAS PWSS | SM/17931 | New | Acceptance cum Formal work order for the work of Yield testing of different Departmentally drilling pin point place of Banksol(T/w-II), Barasol (T/w-II) etc site in Bhelaidiha gp, Binpur-II Block of Jhargram District in Connection to JJM programme under Bankura Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/000334/2024-2025 | 548/BMSD(D) | 19/06/2024 | 19/12/2024 | DEBJYOTI BASU | 0.97 | 0 | 0 | 0
2 | JHARGRAM | Binpur-II | Bankura Mechanical | BANKSOL AND ADJOINING MOUJAS PWSS | SM/17931 | New | Acceptance cum Formal work order for the work of Supply and delivery of Cutting tools, Lubricants etc for KLR Rig machine in connection with Jal Jeevan Mission programme at Jhargram under Bankura Mechanical Division ,PHE Dte. |  |  | ORD/000615/2023-2024 | 2087/BMD | 12/09/2023 | 10/01/2024 | SUDIP ENGINEERING CO | 23.85 | 0 | 0 | 100
3 | JHARGRAM | Binpur-II | Bankura Mechanical | BANKSOL AND ADJOINING MOUJAS PWSS | SM/17931 | New | Acceptance cum Formal work order for the work of Providing man power engagement and Driver for construction of R.B.T.W in connection to JJM programme in Jhargram District by Rig unit KLR at B.M.S.D(D) under Bankura Mechanical Division P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/001226/2023-2024 | 252/BMSD(D) | 13/03/2024 | 31/03/2024 | CHAKRABORTY MINING & ENGINEERING. | 0.97 | 0 | 0 | 100
4 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | BANKSOL AND ADJOINING MOUJAS PWSS | SM/17931 | New | New connection bill for Barsole in Bheliadiha GP |  |  | BILL/01475/2023-2024 | 77/JMD | 20/03/2024 | 20/03/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
5 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | BANKSOL AND ADJOINING MOUJAS PWSS | SM/17931 | New | New connection bill for Banksole in Bheliadiha GP |  |  | BILL/01476/2023-2024 | 78/JMD | 20/03/2024 | 20/03/2024 | WBSEDCL | 0.21 | 0 | 0 | 0
6 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | BANKSOL AND ADJOINING MOUJAS PWSS | SM/17931 | New | New service connection charges |  |  | BILL/01075/2023-2024 | 10/JMD | 05/01/2024 | 05/01/2024 | WBSEDCL | 0.42 | 0 | 0 | 0
7 | JHARGRAM | Binpur-II | Jhargram Mechanical Division | BANKSOL AND ADJOINING MOUJAS PWSS | SM/17931 | New | Erection & commissioning of 22 (twenty two) nos. standalone piped water supply schemes by constructing pump house, community tank, laying of distribution pipeline for providing FHTC with supply, delivery and installation of pumping machineries & allied Electro-Mechanical accessories at Bhelaidiha G.P. in place of (Chainbera Zone-III Joypur (TSM/015566), Hijla (TSM/014334) and Banksol (TSM/015563) w/s schemes under Binpur-II Block of Jhargram District under Jhargram Mechanical Division, PHE Dte. | DIC(D)_MMSD(D) | Junior Engineer | ORD/000322/2023-2024 | 3015/JMD | 20/10/2023 | 22/12/2025 | CONCORD ENGINEERING | 621.67 | 0 | 0 | 25
Total | [13 empty] | 648.29 | 0 | 0